## Slide 1
MOps Weekly Review
Team Performance, Campaign Results & Strategic Roadmap
September 10, 2026 | Project Review Meeting

## Slide 2
RETROSPECTIVE
Reviewing Last Week
Sep 3 – Sep 9, 2026

## Slide 3
RETROSPECTIVE
Executive Summary
Source: Asana [MOps] Intake, live query 2026-09-10
3
33 tasks completed
33 tasks shipped · 27 new SFDC campaigns launched, 2 already showing member activity (287 contacts/responses) · 0 top-level tickets closed this period, so SLA can't be scored against a full ticket this week
This was a build week, not a close-out week: every one of the 33 completions was a sub-task inside a multi-step campaign or event already in flight (Partner Master Class webinar, 5 new SFDC campaign builds, 2 list uploads) rather than a finished top-level ticket — so this period has no on-time-SLA score (see slide 7). Five new SFDC campaigns and 2 event campaigns from the period are already live; two are showing real engagement (287 contacts/responses combined), the rest are 0-6 days old and too new to judge. Aayushi carries 18 of the 44 look-ahead tasks — watch that load into next week.

## Slide 4
RETROSPECTIVE
Completed Tasks by Team Member
Source: Asana search_tasks, completed_on Sep 3–9 2026
4
Harish Pandey
7
Aayushi Sharma
5
Felipe Tencio
4
Jennifer S.
0
+ 17 completions by cross-team collaborators (web/creative stakeholders on shared sub-tasks) and unassigned placeholder tasks — not counted against MOPS core team capacity.

## Slide 5
RETROSPECTIVE
Emails Sent Last Week
Source: Asana milestone sub-tasks, Project Type = Email, due_on Sep 3–9
5
SEND / CAMPAIGN NAME | SEND DATE | REGION/AUDIENCE
DAM Workshop Boston — Email Send 03 | Sep 7, 2026 | Region/Audience not set on task
London Partner Party — Email 3 Send | Sep 4, 2026 | Region/Audience not set on task
Region/Audience is not populated on either task — same gap flagged in prior weeks' reviews.

## Slide 6
RETROSPECTIVE
Campaign Performance (Salesforce)
Source: SOQL — Campaign WHERE CreatedDate=LAST_N_DAYS:7 OR StartDate=LAST_N_DAYS:7
6
CAMPAIGN | MEMBERS | RESPONSES | RESP. RATE | OPPS/PIPELINE
em_webinar_dxo_26_q3_partner_0_Acquia | 286 | 286 | 100% | 0 / $0
evt_webinar_dxo_26_q3_partner_0_DAM Updates Pa | 1 | 1 | 100% | 0 / $0
Period roll-up: 27 campaigns created/started this period · 287 contacts/responses · 0 opportunities · $0 pipeline
The other 25 campaigns from this period show 0 members/responses — all are 0-8 days old (created/started this week), so this reads as "too new to have activity" rather than a problem. See slide 17 for the 2 that are old enough to actually flag.

## Slide 7
RETROSPECTIVE
SLA & Cycle Time
Source: Asana search_tasks — parent/is_subtask fields, 2026-09-10
7
No top-level [MOPs] Intake tickets were completed this period.
All 33 completions this period were sub-tasks inside campaigns/events opened in prior periods — the on-time-SLA metric (created→completed vs. the per-type SLA clock) needs a completed top-level ticket to score against, so there is nothing to compute this week. This is the same top-level-vs-subtask measurement question flagged in the 2026-09-03 run as still open with Jennifer/Aayushi. No rush/late flags to report either, for the same reason. Recommend confirming with Jennifer whether subtask-level cycle time (e.g. campaign-build steps) should get its own SLA definition rather than borrowing the ticket-level one.

## Slide 8
RETROSPECTIVE
Lead Weekly Wins
Aayushi Sharma — lead
8
Win 1
5 SFDC campaign builds shipped this week across FOST Paris, OnDAM Paris, Connect 2026, DigiCol26, and DrupalCon Rotterdam — the backbone of Q4 event pipeline.
Win 2
Partner Master Class webinar moved through 12 build steps in a single week (landing page live, form tested, banner requested, audience selected) — on track for its Sep 14 target.
Win 3
287 contacts/responses logged this period on the two campaigns already sending (em_webinar_dxo Acquia partner send + DAM Updates Partner Master Class Zoom webinar).

## Slide 9
RETROSPECTIVE
Team Performance Highlights
Non-lead team members
9
Harish Pandey
Cleared 7 completions incl. 3 SFDC campaign builds (FOST Paris, OnDAM Paris, DrupalCon Rotterdam)
Carries 10 of 44 look-ahead items
Felipe Tencio
4 completions, all audience/list work (Atlanta Tech Week, Fintech Summit MX, DrupalCamp Italy)
7 look-ahead audience-report items queued

## Slide 10
LOOK AHEAD
Planning Next Week
Sep 10 – Sep 21, 2026

## Slide 11
LOOK AHEAD
Upcoming Tasks by Team Member
Source: Asana search_tasks, due_on Sep 10–21 2026
11
Aayushi Sharma
18
Harish Pandey
10
Felipe Tencio
7
Jennifer S.
0
Total Capacity Required: 44 Tasks (incl. 9 cross-team/unassigned items not on this chart)

## Slide 12
LOOK AHEAD
Upcoming Email Sends Next Week
Source: Asana milestone sub-tasks, Project Type = Email, due_on Sep 10–21
12
SEND / CAMPAIGN NAME | SEND DATE | REGION/AUDIENCE
Webinar w/ Hounder & LADWP — Email Invite 2 | Sep 10, 2026 | Region/Audience not set on task
Partner Summer Party (London) — Email 4 Send | Sep 11, 2026 | Region/Audience not set on task
Drupal Canvas/Agentic Content — Email 2 Promo | Sep 11, 2026 | Region/Audience not set on task
DAM New Features Webinar — Registration Email Send 2 | Sep 15, 2026 | Region/Audience not set on task
DAM New Features Webinar — Registration Email Send 3 | Sep 15, 2026 | Region/Audience not set on task
Drupal Canvas/Agentic Content — Email 3 Promo | Sep 14, 2026 | Region/Audience not set on task
DrupalCamp Italy Wrap Around — Email 1 | Sep 17, 2026 | Region/Audience not set on task
Webinar w/ Hounder & LADWP — Email Invite 3 | Sep 17, 2026 | Region/Audience not set on task
DrupalCon Rotterdam Partner Summit — Email 3 Send | Sep 16, 2026 | Region/Audience not set on task
Flagged clashes:
• Sep 11: London Partner Party Email 4 + Drupal Canvas Email 2 Promo — same day, different campaigns (audience field blank, can't confirm true overlap)
• Sep 15: DAM New Features Webinar Registration Sends 2 AND 3 both due the same day — looks like a scheduling inconsistency within the same campaign, worth a sanity check with Aayushi
• Sep 17: DrupalCamp Italy Email 1 + Hounder/LADWP Webinar Email Invite 3 — same day, different campaigns

## Slide 13
LOOK AHEAD
Priority Pipeline
Aayushi Sharma — lead
13
Aayushi Sharma (lead)
18 of 44 look-ahead tasks — heaviest load again this cycle; DAM New Features Webinar registration sends + DigiCol26 emails are the near-term crunch (Sep 15-16).

## Slide 14
LOOK AHEAD
Upcoming Strategic Priorities
Non-lead team members
14
Harish Pandey
10 look-ahead tasks: 2 list uploads (BBDD SOLA26/BR26, due Sep 14), DrupalCon Rotterdam partner summit sends, September partner newsletter (Sep 17)
Felipe Tencio
7 look-ahead audience-report tasks feeding Aayushi's and Harish's email sends — Henry Stewart DAM NY, DigiCol26, DrupalCon Rotterdam

## Slide 15
LOOK AHEAD
Active Sub-Projects
Source: Asana [MOps] Intake, grouped by sub-category
15
SUB-CATEGORY | CORE ACTIVITY | STATUS
Webinar Requests | Partner Master Class webinar — 12 of ~20 template steps completed this period (landing page, form test, push-live, banner, planning doc, audience, Zoom edit, kickoff, campaign naming) | 
SFDC & UTM | 5 SFDC campaign builds completed (FOST Paris, OnDAM Paris, Connect 2026, DigiCol26, DrupalCon Rotterdam) | 
List Uploads | 2 completed (Atlanta Tech Week, Fintech Summit MX); 3 more in flight (BBDD SOLA26, BBDD BR26, Febraban BR) | 
Email Requests | 2 sends shipped, 9 queued for next 1.5 weeks — see slides 5 & 12 | 
IN PROGRESS
ON TRACK
ON TRACK
ON TRACK

## Slide 16
LOOK AHEAD
Incomplete Tickets
Source: Asana MOPS-Status = Blocked / Require Info / Waiting for Feedback
16
TICKET | ASSIGNEE | MISSING INFO | PRIORITY
Zapier integration - LinkedIn | Unassigned | No scope/owner for 8 months | Not set
[Event Name] Pre Event Marketing Emails | Unassigned | [Event Name] placeholder never filled in; overdue since Jul 31 | Not set
Optimize Starter — ACP Renewal Cadence | Karen Plant | Waiting on Nate for report/audience | Not set
SFDC List Upload — BBDD SOLA26 | Harish Pandey | Waiting for Feedback, due Sep 14 | Not set
SFDC List Upload — BBDD BR26 | Harish Pandey | Waiting for Feedback, due Sep 14 | Not set
Create contact list — ICP 2026 | Unassigned | Waiting for Feedback since Feb 2026 (~7mo) | Not set
Priority field is blank on every one of these tickets in Asana — reported as "Not set," not guessed.

## Slide 17
LOOK AHEAD
Data Hygiene & Recommendations
Source: SOQL Campaign query + campaign-naming/SKILL.md convention check
17
CAMPAIGN / FINDING | ISSUE | FLAG
evt_webinar_dxo_26_q3_partner_0_DAM Update | Created Aug 19 — 15 business days old, still only 1 member | 
em_promo_DrupalCamp Italy Wrap Around Even | Created Sep 2 — ~6 business days old, 0 members | 
demgen_best-platform-for-drupal-north-amer | StartDate is blank | 
Naming pattern (systemic) | 25 of 27 new campaigns use the lowercase snake_case pattern (e.g. demgen_..._q4_26), not the do | 
AT RISK
AT RISK
AT RISK
AT RISK
Recommendations:
1. Confirm the real naming standard: 25 of 27 new campaigns follow a lowercase snake_case convention that isn't Region_Channel_Product_Description_YYYY-Qn — pin down which one is canonical with Jennifer so campaign-naming/SKILL.md matches reality.
2. Chase the DAM Updates Partner Master Class webinar campaign (created Aug 19, still 1 member) — closing this gap unlocks a real read on that campaign's response rate.
3. Resolve the Zapier–LinkedIn integration ticket's 8-month unassigned status — either scope it or move it to Deprioritized so it stops sitting in the open backlog silently.

## Slide 18
Closing / Questions
Next Review: September 17, 2026 | Lead: Aayushi Sharma

## Slide 19
RETROSPECTIVE
Data & Image Sources
19
SOURCE | QUERY | QUERIED
Asana — [MOps] Intake (gid 1205660951274722) | search_tasks (completed_on / due_on filters), get_project (custom fields) | 2026-09-10, live
Salesforce — Campaign | soqlQuery: Campaign WHERE CreatedDate=LAST_N_DAYS:7 OR StartDate=LAST_N_DAYS:7 | 2026-09-10, live
Jira — MOPS project | searchJiraIssuesUsingJql — connector timed out 3x this run | 2026-09-10 — FAILED, not retried further
Gaps stated plainly, not guessed: Jira MOPS project data could not be pulled — the Atlassian MCP connector timed out on 3 consecutive attempts (getAccessibleAtlassianResources); per this skill's no-blind-retry guidance it was not retried a 4th time this run. No Jira-linked bugs/blockers are reflected anywhere in this deck as a result. Region/Audience fields are blank on every email milestone sub-task checked (slides 5 & 12) — stated as a gap, not inferred. This period had zero completed top-level intake tickets, so slide 7's SLA metric could not be computed (see that slide for detail) — not the same as "0% on time." No external images used in this deck; all visuals are native PowerPoint shapes.
Google Slides upload: not attempted this run. The Drive create_file MCP tool only accepts inline base64 content with no chunked/path-based alternative, and this exact deck size has confirmed the same ~350K-output-token wall on 6 consecutive prior runs (2026-07-23, 07-30, 08-13, 08-20, 08-27, 09-03) — see decisions/log.md. Per this run's instructions not to retry a known-broken approach, it was not attempted a 7th time. Deck built and saved locally only; flagged on the #mops-team Slack post.