## Slide 1
MOps Weekly Review
Team Performance, Campaign Results & Strategic Roadmap
August 27, 2026 | Project Review Meeting

## Slide 2
RETROSPECTIVE
Reviewing Last Week
Retro period: Aug 20-26, 2026

## Slide 3
RETROSPECTIVE
Executive Summary
30
Tasks completed
11
SFDC campaigns built
983
Contacts reached (2 live sends)
$5,863
Pipeline / 6 opps attributed
30 tasks completed across the team this week (Aayushi 11, Felipe 11, Harish 6, 1 unassigned, 1 from a cross-listed Creative ticket). Aayushi built 11 new SFDC campaigns; Harish shipped 2 live promotional email sends (August Partner Newsletter, Open Source AI Meet Up) that together reached 983 contacts, drove 6 opportunities (1 won) and $5,863 in attributed pipeline; Felipe delivered 4 Reporting requests and 3 Audience pulls, and cleared two very old backlog tickets (66-98 business days old) along the way.
The average completion took 20.9 business days end-to-end this week, but that number is dominated by 6 legacy backlog items (17-98 business days old) getting closed out, not by new work missing its clock -- excluding those, the real-time average was 9.3 business days. Only 1 of 11 SFDC campaign builds landed inside its 1-2 business day SLA target (9%).
Two tickets remain BLOCKED for 7 and 9.5 months respectively (Zapier-LinkedIn integration; Virtual DAM Workshop NA email request) and need an owner. Aayushi's look-ahead queue is 17 of 31 upcoming tasks (55%) -- see slide 11 and the Data Hygiene recommendations on slide 17.
Source: Asana [MOps] Intake project (search_tasks, completed_on 2026-08-20 to 2026-08-26), queried 2026-08-27. Pipeline/opps from Salesforce Campaign rollups (see slide 6).

## Slide 4
RETROSPECTIVE
Completed Tasks by Team Member
Aayushi Sharma
11
Felipe Tencio
11
Harish Pandey
6
Jennifer S.
0
Team total: 30 completed (+1 unassigned, +1 from a cross-listed Creative ticket, not shown above)
Source: Asana [MOps] Intake, tasks completed 2026-08-20 to 2026-08-26 (includes sub-tasks and email-send milestones). Jennifer had no Asana completions this week but was actively triaging in Slack (assigning Felipe/Aayushi, investigating a Tier 2 MQL scoring gap) -- that work doesn't surface as a task count here.

## Slide 5
RETROSPECTIVE
Emails Sent Last Week
SEND / CAMPAIGN NAME | SEND DATE | REGION / AUDIENCE | OWNER
August 2026 Partner Newsletter | Thu, Aug 20 | Not set on the milestone (see gap note) | Harish
Open Source AI Meet Up - Email Send | Thu, Aug 20 | Not set on the milestone (see gap note) | Harish
[DrupalCon Rotterdam] First Email Send | Tue, Aug 25 | Not set on the milestone (see gap note) | Harish
Source: Asana [MOps] Intake, completed Email-type milestone sub-tasks due 2026-08-20 to 2026-08-26. GAP: the Region/Audience field is not populated on any of these milestones in Asana -- a known data gap flagged in prior weekly reviews, not filled in this run.

## Slide 6
RETROSPECTIVE
Campaign Performance (Salesforce)
These are the only 2 of 59 campaigns (created/started 2026-08-20 to 2026-08-27) with actual member/response data -- the other 57 are new Q3 paid-media flights (Agentic Marketing, Source AI Cites, EDU/FinServ/NGO, Content Chaos Quiz, DrupalCamp/DAM Workshop event campaigns) that started 0-5 days ago and have zero members by design, not by neglect.
CAMPAIGN | CONTACTS/LEADS | RESPONSES | RESP. RATE | OPPS / WON | PIPELINE $
em_ac_August 2026 partner newsletter_2026_q3 | 803 / 146 | 949 | 99.9% | 2 / 0 | $1,554
em_promo_open_source AI Meet Up_2026_q3 | 180 / 1 | 181 | 100% | 4 / 1 | $4,310
PERIOD TOTAL (2 campaigns with delivered sends) | 983 / 147 | 1,130 | - | 6 / 1 | $5,863
Source: Salesforce SOQL on Campaign (CreatedDate/StartDate = LAST_N_DAYS:7) and CampaignMember, queried 2026-08-27. Response rate = Responses / Contacts+Leads. "Resp. Rate" >100% on the AI Meet Up row reflects multiple response touches per member, not a data error.

## Slide 7
RETROSPECTIVE
SLA & Cycle Time
No clean "submission date" field exists in Asana separate from task-creation date, so cycle time (created -> completed, business days) is reported as the SLA proxy, per the sla-watchdog SOP.
SFDC Campaign creations (target: 1-2 business days)
- 1 of 11 completed within SLA (9%) -- avg cycle time 19.0 business days.
- Fastest: "Campaign Build" (Aayushi), same-day (0 bd) -- the one on-time build.
- Slowest: New England Drupal Camp SFDC (51 bd, unassigned) and [Event Name] SFDC Campaign (20 bd, Aayushi).
Backlog clearances this week (not new-request SLA misses)
- [Event Name] Post-Event Email Audience Report x2 -- 98 business days old (created April 6).
- [Event Name] Pre-Event Email Audience Report -- 48 business days old (created June 15).
- Gartner IT Symposium SFDC (Email-type) -- 77 business days old (created May 8).
- Excluding these 4 plus 2 more >=20bd outliers, real-time average cycle time was 9.3 business days across the other 23 completions.
Rush / Late
- No tickets flagged "Out of SLA/Rush = Yes" among this week's completions.
Source: Asana [MOps] Intake created_at/completed_at, computed 2026-08-27. SLA targets per sla-watchdog SKILL.md. Business-day math excludes weekends only (no holiday calendar).

## Slide 8
RETROSPECTIVE
Lead Weekly Wins -- Aayushi Sharma
SFDC Campaigns Delivered (11)
- Drupal Ads Carousel, Federal ABM/LinkedIn, Competitor Search (WORDPRESS), Pantheon Compete (Google) -- 4 competitive/paid-media campaign builds.
- DAM Workshop NYC + DAM Workshop DC -- both event campaigns built same week.
- Drupal 12 US Holiday Party, [Event Name] SFDC Campaign, New England Drupal Camp, Gartner IT Symposium (Email-type), "Campaign Build" (multi-campaign request).
Backlog Cleared
- Gartner IT Symposium -- 77 business days overdue, closed out this week.
- [Event Name] SFDC Campaign -- 20 business days overdue, closed out this week.
Cross-team
- Publicly thanked Felipe in #mops-team (2026-08-25) for picking up remaining Agentic/Source AI/Velocity campaigns.
Source: Asana [MOps] Intake completions 2026-08-20 to 2026-08-26; #mops-team Slack history.

## Slide 9
RETROSPECTIVE
Team Performance Highlights
Harish Pandey
- 2 live email sends: Partner Newsletter (949 responses, $1,554 pipeline) + Open Source AI Meet Up (181 responses, 1 won opp, $4,310 pipeline).
- [DrupalCon Rotterdam] first promo email sent on schedule (Aug 25).
- List Upload: partner-newsletter email additions completed.
Felipe Tencio
- 4 Reporting deliverables: Report Sign Off, Data Validation, Report Creation, Best Platform for Drupal H2 ICP Contact Report.
- 3 Audience pulls: Scottish Web Folk (Higher Ed), DrupalCon Rotterdam Cust/Prospect, SHSMD Speakers list.
- Cleared 2 very old [Event Name] audience-report backlog items (66 and 98 business days old).
Jennifer Schroback
- 0 Asana completions this week -- she owns the 3 no-pattern types (IT/Integration, Automations|Martech, UAT), none closed this period.
- Active in #mops-team: assigned Felipe/Aayushi to open campaign requests, flagged that imported leads aren't being behaviorally scored since Jul/Aug.
- No task-count proxy captures this triage/investigation work -- noted rather than estimated.
Source: Asana [MOps] Intake completions + assignments; #mops-team Slack (2026-08-25 to 08-27).

## Slide 10
LOOK AHEAD
Planning Next Week
Look-ahead period: Aug 27 - Sep 6, 2026

## Slide 11
LOOK AHEAD
Upcoming Tasks by Team Member
Aayushi Sharma
17
Unassigned
6
Felipe Tencio
4
Harish Pandey
3
Jennifer S.
0
Total Capacity Required: 31 Tasks (+1 from a non-MOPS-team assignee, not shown above)
Source: Asana [MOps] Intake, open tasks due 2026-08-27 to 2026-09-06, queried 2026-08-27. Aayushi carries 55% of all upcoming work; 6 tasks (19%) have no owner at all.

## Slide 12
LOOK AHEAD
Upcoming Email Sends Next Week
⚠ Same-day flag: DrupalCamp Italy Email 1 and Partner Summer Party London Email 3 both send Sep 3 from Harish -- different events, but worth a quick check that audiences don't overlap and capacity isn't double-booked.
SEND / CAMPAIGN NAME | SEND DATE | REGION / AUDIENCE | OWNER
[NAME] Registration Email 1 (webinar TBD) | Thu, Aug 27 | Not set (placeholder name -- see gap note) | Aayushi
[DrupalCon Rotterdam] Partner Summit Email 2 | Wed, Sep 2 | Not set on the milestone | Harish
DrupalCamp Italy Wrap Around Event Email 1 | Thu, Sep 3 | Not set on the milestone | Harish ⚠
Partner Summer Party - London Email 3 | Thu, Sep 3 | Not set on the milestone | Harish ⚠
Source: Asana [MOps] Intake, incomplete Email-type milestone sub-tasks due 2026-08-27 to 2026-09-06. GAP: Region/Audience not populated on any milestone (same gap as slide 5).

## Slide 13
LOOK AHEAD
Priority Pipeline -- Aayushi Sharma
17 of 31 upcoming team tasks (55%) -- the heaviest load on the team by a wide margin.
Due Aug 27 (today) -- 2 still marked "Require Information/Description"
- Henry Stewart DAM NY 2026 SFDC Campaign -- awaiting requester info, due today.
- MAICON SFDC Campaign -- form largely blank, due today.
- BPFD Intentsify SFDC Campaign, Campaign creation, [NAME] Registration Email 2 -- also due today.
Due Sep 1-4
- Content Marketing World, DigiCol26, Connect 2026 SFDC campaigns.
- Drupal Canvas and Agentic Content: Email 1 Promo + Webinar Email Creation.
- DrupalCamp Colorado, DAM Workshop NYC/DC pre-event marketing emails.
Source: Asana [MOps] Intake, open tasks assigned to Aayushi Sharma due 2026-08-27 to 2026-09-06.

## Slide 14
LOOK AHEAD
Upcoming Strategic Priorities
Harish Pandey
- 3 email sends queued: Partner Summit Email 2 (Sep 2), DrupalCamp Italy Email 1 (Sep 3), Partner Summer Party London Email 3 (Sep 3, same-day as Italy send).
Felipe Tencio
- 4 audience/pre-event report pulls due Aug 28-Sep 2: [Event Name] Pre-Event Report (x2), DAM Workshop NYC Pre-Event Report, Partner Summit organic social request (cross-listed, not MOPS-owned).
Unassigned (6 tasks, needs owner)
- Drupal Canvas and Agentic Content: MOPs Add CID to Form, Create Webinar Landing Page (due Aug 28); Push Page Live, Test Form (due Aug 31).
- [Event Name] Field Update, [Event Name] Sales Emails (due Sep 1).
Source: Asana [MOps] Intake, open tasks due 2026-08-27 to 2026-09-06, queried 2026-08-27.

## Slide 15
LOOK AHEAD
Active Sub-Projects
SUB-CATEGORY | CORE ACTIVITY THIS PERIOD | STATUS
SFDC & UTM Campaigns | 11 built this retro period; 8 more queued for look-ahead (Henry Stewart DAM NY, MAICON, BPFD Intentsify, Content Marketing World, DigiCol26, Connect 2026, +2) | ON TRACK
Email Requests | 3 sends delivered this period (983 contacts); 4 sends queued for next period incl. a same-day pair on Sep 3 | IN PROGRESS
Webinar Requests | No pure Webinar Request-type tickets closed or due this period -- Drupal Canvas/Agentic webinar email creation is in progress under Email/SFDC types instead | READY
List Uploads | 1 completed (partner newsletter list addition); none queued for next period | ON TRACK
Audiences / Reporting | 7 completed (4 Reporting, 3 Audience pulls, incl. 2 items 66-98 business days overdue); 4 more queued | IN PROGRESS
Source: Asana [MOps] Intake Project Type field, retro + look-ahead windows, queried 2026-08-27.

## Slide 16
LOOK AHEAD
Incomplete Tickets
TICKET | ASSIGNEE | MISSING INFO | PRIORITY
Zapier integration - LinkedIn | Unassigned | BLOCKED 7 months (created Jan 12) -- SFDC campaign ID and 3 lead-gen forms on file, no stated blocker in Notes | BLOCKED
Virtual DAM Workshop NA - Email Request | Unassigned | BLOCKED 9.5 months (created Nov 10) -- creative + planning doc linked, no stated blocker in Notes | BLOCKED
Henry Stewart DAM NY 2026 SFDC Campaign | Aayushi | Campaign Currency, Region, Cost, Product Cloud Interest all blank on the form; due today | AT RISK
MAICON SFDC Campaign | Aayushi | Entire request form blank except name; due today | AT RISK
DigiCol26 SFDC Campaign | Aayushi | Entire request form blank except a partial notes string | NEEDS INFO
Gartner IT Symposium Post-Event Marketing Emails | Aayushi | Awaiting requester copy/direction + banner asset for subtask expansion | NEEDS INFO
Optimize Starter upon ACP Renewal - Email Cadence | Karen Plant | Awaiting confirmed ACP-renewal report/segment from Nate; open since 2025-08-07 | NEEDS INFO
Source: Asana [MOps] Intake, MOPS-Status = Blocked (2) or Require Information/Description (9, top 5 shown), queried 2026-08-27. "Missing Info" quoted from each task's own Notes/form fields.

## Slide 17
LOOK AHEAD
Data Hygiene & Recommendations
Flagged this period
- Naming drift: none of the 59 campaigns created/started this period follow the Region_Channel_Product_Description_YYYY-Qn convention -- 3 different legacy patterns in active use (em_ac_..., ev_conference_dc_..., Social_WW_src_...). Advisory, not a hard fail.
- 2 tickets BLOCKED with no stated reason in Notes for 7 and 9.5 months (Zapier-LinkedIn integration; Virtual DAM Workshop NA email).
- Jira MOPS-659156 (Click-ID fields not flowing Campaign Member -> Lead/Contact) remains Need Info/Blocked, unassigned action beyond Jennifer -- recurring across multiple weekly reviews.
- Email-send milestones (5 this period) carry no Region/Audience value in Asana -- a gap flagged since 2026-07-13 and still open.
Recommendations
- 1. Resolve the 2 stale BLOCKED tickets (7 and 9.5 months old) -- clears the oldest items on the board and unblocks Priyanka's LinkedIn lead-gen Zap and the DAM Workshop NA send.
- 2. Rebalance Aayushi's 17-task look-ahead load (55% of all upcoming work) -- moving even 3-4 SFDC campaign builds to Harish or Felipe would cut it to ~13 and reduce risk on the 2 Aug-27-dated tickets still marked Require Info.
- 3. Assign the 6 unassigned look-ahead tasks (19% of upcoming work), especially the 4 Drupal Canvas/Agentic Content MOPs form-and-landing-page items due Aug 28-31 -- unowned work this close to due date is a launch risk.
Source: Salesforce Campaign naming audit (this period's 59 campaigns); Asana MOPS-Status field; Jira MOPS-659156; Asana email-milestone custom fields. Queried 2026-08-27.

## Slide 18
Questions?
Thank you
Next Review: September 3, 2026 | Lead: Aayushi Sharma

## Slide 19
APPENDIX
Data & Image Sources
Connectors queried (2026-08-27, this run)
- Asana MCP -- [MOps] Intake project (gid 1205660951274722): search_tasks for retro completions, look-ahead due tasks, and Email-type milestones (sent + upcoming).
- Salesforce MCP -- soqlQuery on Campaign (CreatedDate/StartDate = LAST_N_DAYS:7) and CampaignMember (GROUP BY CampaignId, Status).
- Atlassian (Jira) MCP -- searchJiraIssuesUsingJql, project = MOPS, created or updated since 2026-08-20.
- Slack MCP -- slack_read_channel on #mops-team, for the Lead Weekly Wins / Team Highlights narrative context (not a data source for counts).
Known gaps -- stated plainly, not guessed around
- No clean "submission date" field distinct from Asana task-creation date -- cycle time (created->completed) used as the SLA proxy throughout, per sla-watchdog SOP.
- Region/Audience not populated on any Email-type milestone sub-task (5 of 5 checked this period).
- Google Slides upload not attempted this run -- see the #mops-team post and decisions/actions.md for why (known base64 output-token wall, confirmed 4 consecutive weeks: 2026-07-23, 07-30, 08-13, 08-20).
Images
- No external images used -- all charts/tables are native PowerPoint shapes built from the queried data above; no attribution required.
Deck built locally: outputs/weekly-review/MOps_Weekly_Review_2026-08-27.pptx