## Slide 1
MOps Weekly Review
Team Performance, Campaign Results & Strategic Roadmap
October 1, 2026 | Project Review Meeting

## Slide 2
RETROSPECTIVE
Reviewing Last Week
September 24 – September 30, 2026

## Slide 3
RETROSPECTIVE
Executive Summary
45 tasks completed (8 tickets + 37 sub-tasks) · 17 Salesforce campaigns active, 11,363 responses · $5,814 pipeline from 1 won opportunity
A steady week dominated by DrupalCon Rotterdam (Sept 28–Oct 1) wrap-up activity and two live DAM/webinar nurtures. Harish carried 20 of 45 completions (44%), mostly Rotterdam partner-summit sends and the HS/Beyond Portals nurture builds. Campaign volume returned to a normal 17/week after last cycle's 123-campaign paid-media batch. SLA signal is thin this week — of 8 top-level completions, 7 are Email/Nurture types whose SLA clock anchors on scheduled send date rather than ticket completion, so a clean % can't be computed from completion data alone; the team's own Out-of-SLA/Rush field shows 3 within target, 1 rush (VCCP prospect email), 4 unmarked.
Source: Asana [MOPs] Intake (search_tasks, completed_on 2026-09-24..2026-09-30) · Salesforce Campaign SOQL · queried 2026-10-01

## Slide 4
RETROSPECTIVE
Completed Tasks by Team Member
Harish Pandey
20
Felipe Tencio
9
Aayushi Sharma
8
Unassigned
5
Nick Stalford
1
Karen Plant
1
Jennifer S.
1
Source: Asana [MOPs] Intake, search_tasks completed_on 2026-09-24..2026-09-30 (top-level + sub-tasks) · 45 total

## Slide 5
RETROSPECTIVE
Emails Sent Last Week
SEND / CAMPAIGN NAME | SEND DATE | REGION / AUDIENCE
Beyond Portals email #1 (DAM + Source attach) – Send | Sep 23 | Beyond Portals nurture — no Region/Audience field in Asana
HS Webinar Sept 24 – Email invite 2 | Sep 23 | HS Webinar — no Region/Audience field
DrupalCamp Italy Wrap Around Event Email 1 | Sep 24 | DrupalCamp Italy — no Region/Audience field
EDUCAUSE Wrap Around with Hounder – Send | Sep 28 | EDUCAUSE — no Region/Audience field
DrupalCon Rotterdam Partner Summit Email 4 Send | Sep 28 | DrupalCon Rotterdam — no Region/Audience field
DAM Workshop DC Pre Event Marketing Email Send | Sep 29 | DAM Workshop DC — no Region/Audience field
[Event Name] Post Event Marketing Emails Test | Sep 29 | Placeholder-name ticket — live substitution bug, flagged below
Acquia TV University of East London | Sep 30 | University of East London — no Region/Audience field
Source: Asana Email-type milestone sub-tasks due 2026-09-24..2026-09-30, completed · no Region/Audience custom field exists on the board (gap, same as prior weeks)

## Slide 6
RETROSPECTIVE
Campaign Performance (Salesforce)
CAMPAIGN | MEMBERS | RESPONSES | RESP. RATE | LEADS / CONTACTS
em_promo_vccp_campaign_prospect email 1 | 8,126 | 8,126 | 100% | 6,169 / 1,957
em_promo_src_26_q4_atv_university_of_east_london | 2,766 | 2,766 | 100% | 149 / 2,617
em_promo_EDUCAUSE Wrap Around with Hounder_invite | 288 | 288 | 100% | 1 / 287
em_promo_dam_26_q4_DAM Workshop DC | 149 | 149 | 100% | 0 / 149
NA_Webinar_DC_LADWP Webinar with Hounder Sep | 33 | 33 | 100% | 24 / 9
NA_Evt_Src_AtlantaMarketingLeadershipDinner | 1 | 1 | 100% | 0 / 1
em_followup_partner summit DrupalCon Rotterdam | 0 | 0 | — | 0 / 0
vccp_na/uk-paidsocial-source-meta (2 campaigns) | 0 | 0 | — | 0 / 0
evt_* DrupalCon Rotterdam + FOST Paris (8 campaigns) | 0 | 0 | — | 0 / 0
Period roll-up: 17 campaigns · 6,343 leads + 5,020 contacts (11,363 total members) · 11,363 responses · 12 opportunities, 1 won · $5,814.08 attributed pipeline
Source: Salesforce SOQL, Campaign WHERE CreatedDate=LAST_N_DAYS:7 OR StartDate=LAST_N_DAYS:7 · queried 2026-10-01 · Response Rate = Responses/Members, only shown where Members>0

## Slide 7
RETROSPECTIVE
SLA & Cycle Time
8 top-level tickets completed this week. Team's own Out-of-SLA/Rush field: 3 within SLA · 1 rush (out-of-SLA) · 4 unmarked.
TICKET | PROJECT TYPE | CREATION→COMPLETION | OUT-OF-SLA/RUSH FLAG
Acquia TV University of East London | Email/Nurture | 7 bd | No (within SLA)
Beyond Portals email nurture (DAM + Source attach) | Email/Nurture | 5 bd | Unmarked
EDUCAUSE Wrap Around with Hounder | Email/Nurture | 5 bd | No (within SLA)
HS Webinar Sept 24 Email(s) Only + SFDC Campaign | Email/Nurture | 10 bd | Unmarked
VCCP campaign - Prospect email number 1 | Email/Nurture | 2 bd | Yes (rush)
Email(s) Only + SFDC Campaign (5 Days) | Other | 8 bd | Unmarked
[TEST RUN] SFDC Campaigns (multiple) - DrupalCon Rotterdam | SFDC Campaigns (multiple) | 40 bd (stale backlog item) | Unmarked
Terminus Access | Other | 118 bd (stale backlog item) | No (within SLA)
Avg cycle time: 6.2 bd excluding 2 stale backlog items (24.4 bd including them). No SFDC-Campaign-only new creation to test the 1-bd target this week.
Gap: Email-type SLA anchors on scheduled send date per sla-watchdog, not ticket-completion date — creation→completion is a proxy, not a direct SLA measure. Source: Asana custom fields, read 2026-10-01

## Slide 8
RETROSPECTIVE
Lead Weekly Wins — Aayushi Sharma
Campaign builds
Acquia TV University of East London fully built and live — 2,617 contacts reached, 8 opportunities, 1 won ($3,683 pipeline).
Event support
DAM Workshop DC pre-event email build + send; Atlanta Marketing Leadership Dinner campaign & form creation shipped.
Reporting
SCSM Innovation Session Marketing Nurture performance report delivered.
Source: Asana [MOPs] Intake, Aayushi Sharma completions 2026-09-24..2026-09-30 · Salesforce campaign cross-reference

## Slide 9
RETROSPECTIVE
Team Performance Highlights
Harish Pandey
Carried 20 of 45 completions (44%) — DrupalCon Rotterdam partner-summit sends, EDUCAUSE wrap-around, HS Webinar + Beyond Portals nurture builds.
Felipe Tencio
9 completions — audience/list pulls across DrupalGovCon, EDUCAUSE, VCCP, and the DAM Workshop DC pre-event audience report.
Nick Stalford / Karen Plant
Supporting creative + copy: SHARP Webinar banner request (Nick); Beyond Portals email copy (Karen).
Source: Asana [MOPs] Intake completions by assignee, 2026-09-24..2026-09-30

## Slide 10
LOOK AHEAD
Planning Next Week
October 1 – October 10, 2026

## Slide 11
LOOK AHEAD
Upcoming Tasks by Team Member
Harish Pandey
13
Aayushi Sharma
12
Unassigned
5
Felipe Tencio
3
Nicole Ngoon
1
Nick Stalford
1
Karen Plant
1
Jennifer S.
1
Total Capacity Required: 37 Tasks
Source: Asana [MOPs] Intake, open tasks due 2026-10-01..2026-10-10

## Slide 12
LOOK AHEAD
Upcoming Email Sends Next Week
SEND / CAMPAIGN NAME | SEND DATE | OWNER / AUDIENCE
GAIN Interact Event 2026 - HTMLs Email 1 | Oct 6 | Harish Pandey — ⚠ same date as UCISA send below
[UCISA email Q3] - Membership email send | Oct 6 | Harish Pandey — ⚠ same date, same owner as GAIN send
DrupalCamp Italy Wrap Around Event Email 2 | Oct 8 | Harish Pandey
[DAM New Features Partner Webinar] Registration Email Send 2 | Oct 8 | Aayushi Sharma
⚠ OWNER-CAPACITY CLASH
GAIN Interact Event and UCISA Membership email both land on Harish on Oct 6. No Region/Audience field exists to confirm an audience overlap — flagged as an owner-capacity clash, not a confirmed audience collision.
Source: Asana Email-type milestone sub-tasks, incomplete, due 2026-10-01..2026-10-10

## Slide 13
LOOK AHEAD
Priority Pipeline — Aayushi Sharma
Gartner IT Symposium 2026
SFDC Campaign(s) build due Oct 5 — enterprise IT event, high visibility
SHARP Webinar (EMEA)
Registration emails 1 & 2 (Oct 2, Oct 9), CID-to-form, page push-live Oct 1
Atlanta Marketing Leadership Dinner
Distribution list Oct 2, Promo email 1 send Oct 8
DAM New Features Partner Webinar
Registration email build 3 (Oct 9) + send 2 (Oct 8)
Source: Asana [MOPs] Intake, Aayushi Sharma open tasks due 2026-10-01..2026-10-10

## Slide 14
LOOK AHEAD
Upcoming Strategic Priorities
Harish Pandey
Partner Summit at DrupalCon Rotterdam list upload + follow-up email (Oct 1-2); GAIN Interact and UCISA email sends land same day (Oct 6) — capacity watch.
Felipe Tencio
GAIN Interact audience pull (Oct 2); Carahsoft FedRAMP post-event audience report (Oct 10).
Jennifer Schroback
Add Source & Medium to paid social leads in Salesforce (Oct 2) — attribution-hygiene fix feeding into MOPS-659156.
Source: Asana [MOPs] Intake open tasks by assignee, due 2026-10-01..2026-10-10

## Slide 15
LOOK AHEAD
Active Sub-Projects
SUB-CATEGORY
CORE ACTIVITY
STATUS
Email Requests
Beyond Portals nurture (email 2 due Oct 8); SHARP Webinar + DAM New Features Partner Webinar registration series
IN PROGRESS
SFDC & UTM
Gartner IT Symposium campaign build; Reachdesk Partner SFDC Campaign Request (unassigned)
IN PROGRESS
Webinar Requests
SHARP Webinar (EMEA) — page push-live Oct 1, social copy Oct 5, registration emails Oct 2 & 9
ON TRACK
List Uploads
Partner Summit Rotterdam, HS Webinar DAM, Dinner with Modea, Drupal GovCon, Minnesota Digital Gov Summit — 5 lists due Oct 1-6
IN PROGRESS
Source: Asana [MOPs] Intake, grouped by Project Type / MOPs - Project Subtype, open board as of 2026-10-01

## Slide 16
LOOK AHEAD
Incomplete Tickets
TICKET | ASSIGNEE | MISSING INFO | PRIORITY
Acquia AI GA - Sept 30 a.m. ET | Felipe Tencio | Approval given by Nate Holmes 9/30 21:15 — status field not yet updated to reflect approval | CRITICAL
(blank-name ticket) | Unassigned | Created 9/24, moved straight to Blocked, every field empty — unchanged a full week later | BLOCKED
[Event Name] Pre Event Marketing Emails | Unassigned | Missing email copy — asked 7/13, no response ~80 days | BLOCKED
Zapier integration - LinkedIn | Unassigned | Open since 1/12 (~262 days), deprioritized by design | BLOCKED
Create contact list — ICP 2026 (Drupal/Smarter Content) | Unassigned | Waiting for Feedback since Mar 2026, no due date | BLOCKED
Optimize Starter upon ACP Renewal - Email Cadence | Karen Plant | Awaiting 2026-priorities decision; owner asked if it can be archived | BLOCKED
Source: Asana MOPS- Status = Blocked / Require Information-Description / Waiting for Feedback, read 2026-10-01 via get_task_stories (not guessed)

## Slide 17
LOOK AHEAD
Data Hygiene & Recommendations
Flagged this period
• 0 of 17 campaigns this period match the Region_Channel_Product_Description_YYYY-Qn convention (advisory, not a hard fail).
• vccp_na-paidsocial-source-meta-2026-Q4 (started Sep 14) still has 0 members 11 business days later — the one genuine zero-member hygiene flag this week; the other 10 zero-member campaigns are DrupalCon/FOST Paris event sub-campaigns created Sep 28-Oct 1, too new to flag.
• 90.6% of the 53 open top-level tickets (48 of 53) have null Priority — same gap size as last week (47/52).
• The blank-name Blocked ticket flagged last week (created 9/24) is still blank a full week later — worth a direct nudge, not just another digest line.
Recommendations
→ Fix the vccp_na-paidsocial member sync (Rec 1 of 3) — unlocks response reporting for an 11-business-day-old live campaign.
→ Resolve or delete the blank-name Blocked ticket (Rec 2 of 3) — it's taken a full board slot with zero information for 7 days.
→ Push the 'Acquia AI GA' status field update (Rec 3 of 3) — approval landed 9/30 21:15 but MOPS-Status still reads Waiting for Feedback, risking a false AT-RISK flag on the next sweep.
Source: Salesforce Campaign SOQL naming/member checks + Asana Priority/MOPS-Status field audit, both read 2026-10-01

## Slide 18
Closing / Questions
Next Review: October 8, 2026 | Lead: Aayushi Sharma

## Slide 19
SOURCES
Data & Image Sources
• Asana — [MOPs] Intake (project 1205660951274722): search_tasks for completed (2026-09-24..2026-09-30) and open/due (2026-10-01..2026-10-10) tasks, plus overdue (due before 2026-10-01); get_task_stories for blocked-ticket detail. Queried 2026-10-01 ~14:10 UTC. No gaps — connector worked on first attempt.
• Salesforce — Campaign SOQL (CreatedDate/StartDate = LAST_N_DAYS:7), 17 records. Queried 2026-10-01. No gaps.
• Jira (Atlassian MCP, cloud acquia.atlassian.net) — project MOPS, updated >= -7d: 0 issues touched this period. Verified the 3 previously-flagged blockers (MOPS-659156, -659160, -659161) directly by key — all still open, unchanged since before this retro window.
• Known gaps carried from prior weeks: no Region/Audience field exists anywhere on the Asana board (Slides 5, 12 use ticket/campaign name only); Priority field is 90.6% null (48/53 open tickets); Email-type SLA can't be cleanly measured from ticket completion since the clock anchors on scheduled send date.
• Google Slides upload: not attempted this run — see delivery note in the Slack post and decisions/actions.md (known issue, 10th consecutive occurrence).
• No external images used — all visuals are native shapes built in python-pptx.