## Slide 1
MOps Weekly Review
Team Performance, Campaign Results & Strategic Roadmap
October 8, 2026 | Project Review Meeting

## Slide 2
RETROSPECTIVE
Reviewing Last Week
Oct 1-7, 2026

## Slide 3
RETROSPECTIVE
Executive Summary
22
Tasks Completed
22 tasks shipped (5 requests + 17 sub-tasks)
11 SFDC campaigns launched → 4,974 contacts + 13 leads, 4,985 responses, 51 opportunities (3 won), $110,718 pipeline
100% within SLA this week (4 of 4 scored completions), avg 4.5 business days
A quiet but clean week: every scored request beat its SLA, and the Acquia AI GA send — flagged Rush internally — still cleared the 5-day Email target despite a late copy-approval chain that ran right up to the morning of send. The Partner Summit at DrupalCon Rotterdam fully closed out (SFDC campaign, list upload, and post-event emails all wrapped this week). One new data-hygiene finding: a second duplicate-named ticket pair surfaced (DrupalCon Rotterdam Dinner — 28 Sept 2026, two unassigned copies created 2 minutes apart) — see slide 17.
Source: Asana [MOps] Intake project, live query (search_tasks, completed_on 2026-10-01..2026-10-07).

## Slide 4
RETROSPECTIVE
Completed Tasks by Team Member
Harish Pandey
12
Felipe Tencio
4
Aayushi Sharma
2
Abhinav Dhiman
2
Nick Stalford
1
Nicole Ngoon
1
Team Total: 22 Tasks Completed
Source: Asana [MOps] Intake, live search_tasks (completed=true, completed_on 2026-10-01–2026-10-07).

## Slide 5
RETROSPECTIVE
Emails Sent Last Week
SEND / CAMPAIGN NAME | SEND DATE | OWNER
GAIN Interact Event 2026 – HTMLs Email 1 | Oct 6 | Harish Pandey
[DAM New Features Partner Webinar] Registration Email 1 | Oct 1 | Aayushi Sharma
Source: Asana milestone sub-tasks (resource_subtype=milestone), completed + due in retro window. No Region/Audience field exists on the board (known gap) — Owner shown instead.

## Slide 6
RETROSPECTIVE
Campaign Performance (Salesforce)
CAMPAIGN | LEADS | CONTACTS | RESPONSES | OPPS / WON
NA_Event_Source_Networking Dinner with Modea_2026-Q3 | 12 | 9 | 19 | 0 / 0
EMEA_Email_DXP_GAIN Interact_2026-Q4 | 0 | 179 | 179 | 1 / 0
vccp_global-influencer-drupal-migration-new-acq-101_q4_26 | 1 | 0 | 1 | 0 / 0
em_promo_ai_26_q4_Acquia AI Global Announcement | 0 | 4785 | 4785 | 50 / 3
em_followup_partner summit DrupalCon Rotterdam_2026_q3 | 0 | 1 | 1 | 0 / 0
EMEA_Email_DXP_UCISA Membership send_2026-Q4 | 0 | 0 | 0 | 0 / 0
vccp-global-influencer-source-acq-100_q4_26 | 0 | 0 | 0 | 0 / 0
test_confirmation_ email_setup | 0 | 0 | 0 | 0 / 0
evt_conference_dc_FOST Marketing Reset Paris_2026_q4 | 0 | 0 | 0 | 0 / 0
evt_conference_dc_FOST Drupal AI Summit Paris_2026_q4 | 0 | 0 | 0 | 0 / 0
evt_conference_dc_FOST Paris_2026_q4 | 0 | 0 | 0 | 0 / 0
Period roll-up: 11 campaigns · 13 leads · 4,974 contacts · 4,985 responses · 51 opportunities (3 won) · $110,718 pipeline. Source: Salesforce SOQL, Campaign WHERE CreatedDate/StartDate in 2026-10-01..2026-10-07 (3 additional campaigns created 2026-10-08 excluded — outside this retro window).

## Slide 7
RETROSPECTIVE
SLA & Cycle Time
REQUEST | TYPE | BUSINESS DAYS | RESULT
List Load – Dinner with Modea Sep 28 | List Upload (SLA 7bd) | 6 | WITHIN
List Upload HS webinar – DAM Sept 24 | List Upload (SLA 7bd) | 4 | WITHIN
Acquia AI GA – Sept 30 a.m. ET | Email (SLA 5bd) — flagged Rush | 4 | WITHIN
List Import – LADWP Webinar w/ Hounder | List Upload (SLA 7bd) | 4 | WITHIN
100% within SLA (4 of 4 scored) · avg cycle time 4.5 business days · 0 rush/late breaches. “Partner Summit at DrupalCon Rotterdam” (Event type) excluded — Event/Webinar SLAs anchor to the live event date, not ticket completion, per the SOP. Team's own Out-of-SLA/Rush field on these 5 completions: 3 No, 1 Yes (Acquia AI GA — still made SLA), 1 unmarked.

## Slide 8
RETROSPECTIVE
Lead Weekly Wins
Aayushi Sharma — Team Lead
ON TRACK
• DAM New Features Partner Webinar — Registration Email 1 sent Oct 1; Emails 2 & 3 queued for next week
IN PROGRESS
• SHARP Webinar — social copy/scheduling request completed Oct 5; registration page + confirmation email build continuing
• Churn customer campaign — dynamic Pardot sequence build underway, due Oct 9
Source: Asana, tasks assigned to Aayushi Sharma, live query.

## Slide 9
RETROSPECTIVE
Team Performance Highlights
Harish Pandey
• 12 tasks completed — most of any team member this week
• Fully closed Partner Summit at DrupalCon Rotterdam: SFDC campaign, list upload, and post-event emails all wrapped
• Closed out 3 separate List Upload requests (Modea, HS webinar/DAM, LADWP/Hounder)
Felipe Tencio
• 4 tasks completed, including the Acquia AI Global Announcement audience pull under a same-day Rush flag
• Built the GAIN Interact event audience and the Minnesota Digital Government Summit list upload
Abhinav Dhiman
• Closed 2 long-stale sub-tasks on the LinkedIn Conversions API (CAPI) project — both over 10 months overdue
• Chips away at the IT/Integration backlog (5 open top-level tickets remain in that type)
Source: Asana, live completions by assignee, 2026-10-01 to 2026-10-07.

## Slide 10
LOOK AHEAD
Planning Next Week
Oct 8-17, 2026

## Slide 11
LOOK AHEAD
Upcoming Tasks by Team Member
Aayushi Sharma
13
Unassigned
11
Harish Pandey
7
Felipe Tencio
4
Karen Plant
1
Total Capacity Required: 36 Tasks
Source: Asana [MOps] Intake, live search_tasks (completed=false, due_on 2026-10-08–2026-10-17). 11 of 36 upcoming tasks (31%) carry no assignee — an ownership gap, not an automatic Unassigned bucket.

## Slide 12
LOOK AHEAD
Upcoming Email Sends Next Week
SEND / CAMPAIGN NAME | SEND DATE | OWNER
[DAM New Features Partner Webinar] Registration Email Send 2 | Oct 8 | Aayushi Sharma ⚠
Atlanta Marketing Leadership Dinner Email Promo 1 Send | Oct 8 | Aayushi Sharma ⚠
[SHARP Webinar] Registration Email 1 | Oct 8 | Aayushi Sharma ⚠
DrupalCamp Italy Wrap Around Event Email 2 | Oct 8 | Harish Pandey
[DAM New Features Partner Webinar] Registration Email Send 3 | Oct 14 | Aayushi Sharma
Acquia Festive Party (The Cube, London) Email 1 Send | Oct 14 | Harish Pandey
Beyond Portals email 2 | Oct 15 | Harish Pandey ⚠
DrupalCamp Italy Wrap Around Event Email 3 | Oct 15 | Harish Pandey ⚠
⚠ = same owner has 2+ sends due the same day — see footer.
⚠ Capacity clash: Aayushi owns 3 sends due Oct 8 (same day); Harish owns 2 sends due Oct 15 (same day). No Region/Audience field exists on the board (known gap), so clash is flagged by owner+date, not audience overlap. Source: Asana milestone sub-tasks, due 2026-10-08–2026-10-17.

## Slide 13
LOOK AHEAD
Priority Pipeline
Aayushi Sharma — Team Lead
AT RISK
• 3 sends due Oct 8 (DAM New Features Reg. Send 2, Atlanta Dinner Promo 1, SHARP Webinar Reg. 1) — same-day capacity clash
IN PROGRESS
• SHARP Webinar — Push Page Live + Registration Emails 1 & 2 (Oct 8, Oct 13)
• Churn customer campaign — Pardot Email Build + Dynamic Sequence (Oct 9)
• BPFD - VCCP Email Nurture — SFDC Campaign Request (Oct 9)
READY
• Reachdesk - Partner - SFDC Campaign Request (Oct 8)
• DAM New Features Partner Webinar — Registration Email Build 3 (Oct 9)
Source: Asana, tasks assigned to Aayushi Sharma due 2026-10-08–2026-10-17, live query.

## Slide 14
LOOK AHEAD
Upcoming Strategic Priorities
Harish Pandey
• 2 Festive Party HTML builds in parallel (Paris + The Cube, London) plus a 3rd city ticket (Paris 12 Days of Drupal) all due Oct 8
• DrupalCamp Italy Wrap Around Event — Emails 2 & 3 (Oct 8, Oct 15)
• Beyond Portals email nurture — Email 2 milestone due Oct 15
Felipe Tencio
• 4 pre/post-event audience reports due (Content Marketing World, MAICON, Carahsoft FedRAMP x2)
• Carahsoft Summit on FedRAMP post-event emails due Oct 10
Unassigned Work (flag)
• 11 of 36 look-ahead tasks (31%) have no assignee, incl. both halves of the Dries Prospects + Customer Email Campaign and the duplicate DrupalCon Rotterdam Dinner tickets (slide 17)
• Needs triage before due dates land — not a capacity card, a gap
Source: Asana, live query, 2026-10-08 to 2026-10-17.

## Slide 15
LOOK AHEAD
Active Sub-Projects
SUB-CATEGORY | CORE ACTIVITY | STATUS
Webinar Requests | SHARP Webinar + DAM New Features Partner Webinar — registration email sequences in flight | IN PROGRESS
Email Requests | Churn customer Pardot sequence, Beyond Portals nurture, Dries Prospects + Customer campaign | IN PROGRESS
SFDC & UTM | Reachdesk Partner request + BPFD-VCCP SFDC Campaign Request queued for Oct 8–9 | READY
Event Builds | 3 Festive Party city builds (Paris x2, London) + DrupalCamp Italy wrap-around | IN PROGRESS
List Upload | None pending — all 3 in-flight list uploads closed out this week | ON TRACK
Source: Asana, live query across open sub-tasks grouped by Project Type / naming pattern.

## Slide 16
LOOK AHEAD
Incomplete Tickets
TICKET | ASSIGNEE | MISSING INFO | PRIORITY
(blank — no name set) | Unassigned | Entire ticket is empty (name, notes, Project Type all blank) — created 2026-09-24, still blank 14 days later | BLOCKED
[Event Name] Pre Event Marketing Emails | Unassigned | Promotional email copy never provided; Aayushi's 2026-07-13 ask to the requester is unanswered (~87 days) | REQUIRE INFO
Zapier integration – LinkedIn | Unassigned | Deprioritized pending the Pardot↔LinkedIn direct integration; manual Zapier workaround covers leads meanwhile. Open since 2026-01-12 (~269 days) | BLOCKED
Create contact list – #1 Platform for Drupal ICP / Smarter Content ICP | Unassigned | Requester never answered which data source/fields are needed (asked 2026-02-10). Open since 2026-02-02 (~8 months) | WAITING
Optimize Starter upon ACP Renewal – Email Cadence | Karen Plant | On hold awaiting a 2026-priorities decision (per Karen's comment). Open since 2025-08-07 (~14 months) | REQUIRE INFO
13 top-level tickets are overdue as of today (due before 2026-10-08). Source: Asana, live custom-field query (MOPS-Status) across all 58 open top-level tickets.

## Slide 17
LOOK AHEAD
Data Hygiene & Recommendations
FINDING | DETAIL
Zero-member campaigns, 5+ business days old | 3 of 11 retro-window campaigns (FOST Marketing Reset Paris, FOST Drupal AI Summit Paris, FOST Paris — all started 2026-10-01) still show 0 leads/contacts after 5 business days
Naming convention drift (advisory) | 8 of 11 campaigns launched this week (73%) don't match Region_Channel_Product_Description_YYYY-Qn — only UCISA, GAIN Interact, and Networking Dinner Modea do
New duplicate ticket pair | “DrupalCon Rotterdam Dinner – 28 Sept 2026” exists as 2 separate unassigned tickets, created 2 minutes apart on 2026-10-06 with different due dates (Oct 9 vs Oct 13)
Standing duplicate (unresolved since 2026-09-24) | “Zapier integration – LinkedIn” still exists as 2 open tickets under different owners (unassigned/Blocked, and Jennifer Schroback)
Priority field still mostly null | 54 of 58 open top-level tickets (93%) have no Priority set — up from 90.6% last week as the board grew from 53 to 58
Recommendations: (1) Merge the 2 DrupalCon Rotterdam Dinner tickets before Oct 9 to avoid duplicate list-upload/campaign work for the same event. (2) Check the 3 zero-member FOST Paris campaigns before the conferences run — unlocks real attendee/response tracking for all 3 Paris events this quarter. (3) Force a close-or-continue decision on the two tickets that have sat in “awaiting human input” for 8+ and 14+ months (Create contact list – ICP; Optimize Starter – ACP Renewal) — both have shown up in this review every week since at least August.

## Slide 18
Questions?
Next Review: October 15, 2026 | Lead: Aayushi Sharma

## Slide 19
APPENDIX
Data & Image Sources
QUERIED THIS RUN
• Asana — [MOps] Intake project (gid 1205660951274722), live via MCP: completed tasks 2026-10-01–2026-10-07, open tasks due 2026-10-08–2026-10-17, all 58 open top-level tickets with custom fields, overdue tickets, task notes/comments for blocked items. Queried 2026-10-08.
• Salesforce — Campaign SOQL (Id, Name, Type, Status, StartDate, CreatedDate, member/response/opportunity fields), WHERE CreatedDate/StartDate in the retro window. Queried live 2026-10-08, first attempt succeeded, no connector gaps.
• Jira (Atlassian MCP) — project MOPS, issues created/updated in the last 7 days, plus direct lookup of the 3 previously-flagged blocking issues (MOPS-659156/-659160/-659161). Queried live 2026-10-08, no connector gaps.
• No external images used — all slides built with native python-pptx shapes (no embedded bitmaps).
GAPS / LIMITATIONS
• No Region/Audience field exists anywhere on the Asana board — the email-calendar tables (slides 5 and 12) show Owner in its place, not region, per the standing gap first logged 2026-07-13.
• Priority is null on 93% of the open top-level board (54 of 58) — up from 90.6% last week.
• Google Slides upload not attempted this run. The Google Drive create_file MCP tool only accepts inline base64Content; this deck's base64 payload needs an estimated ~300K+ output tokens to emit in a single tool call, past any single turn's budget. This is the 11th consecutive week confirming the same wall (first logged 2026-07-23, re-confirmed with token-density measurement 2026-07-30, reconfirmed every week since). Deck built locally only — flagged on the #mops-team Slack post.
• MOPS-659156 changed status this week to “Need Info/Blocked” (previously open/unresolved, unchanged status name) — updated 2026-10-06. MOPS-659160 and MOPS-659161 saw no activity in the retro window.