## Slide 1
MOps Weekly Review
Team Performance, Campaign Results & Strategic Roadmap
2026-09-17 | Project Review Meeting

## Slide 2
RETROSPECTIVE
Reviewing Last Week
September 10 – September 16, 2026

## Slide 3
RETROSPECTIVE
Executive Summary
38
Tasks completed this period
38 tasks shipped · 123 SFDC campaigns created (only 3 show real engagement) · 0 of 7 SFDC campaign builds hit the 1-business-day SLA target
A high-volume week driven almost entirely by a 123-campaign paid-media/demand-gen batch load in Salesforce (vccp_/demgen_ prefixes), not by organic intake throughput — Asana completions (38) tracked close to the recent weekly average. Real, attributable results came from a handful of items: the Acquia TV Manifesto Source email drove 495 responses and 4 opportunities, and the EvolveDigital Pre-summit Meetup and Scottish Web Folk Conference email both converted into live SFDC campaigns with member activity. Every one of the 7 SFDC-campaign-only builds completed this period missed its 1-business-day target (avg cycle time 13.6 business days including 2 backlog items dating to July; 4.4bd excluding them) — the recurring SLA gap persists. $0.000152 in attributed pipeline against 3 won opportunities remains a rollup-reliability issue, not a performance one.

## Slide 4
RETROSPECTIVE
Completed Tasks by Team Member
Aayushi Sharma
14
Felipe Tencio
11
Harish Pandey
8
Unassigned
4
Michelle Glass
1
Jennifer Schroback
0
Source: Asana [MOps] Intake — search_tasks, completed_on 2026-09-10..2026-09-16, top-level + sub-tasks (38 total).

## Slide 5
RETROSPECTIVE
Emails Sent Last Week
Send / Campaign Name | Send Date | Region / Audience
Drupal Canvas and Agentic Content: Email 2 Promo | 2026-09-10 | Not tracked (no field)
Webinar with Hounder and LADWP Email invite 2 | 2026-09-11 | Not tracked (no field)
Drupal Canvas and Agentic Content: Email 3 Promo | 2026-09-14 | Not tracked (no field)
Partner Summer Party - London Email for Registrant | 2026-09-15 | Not tracked (no field)
4 email milestone sub-tasks completed this period.
Source: Asana milestone sub-tasks, Project Type = Email(s) only | Nurture Sequences, resource_subtype=milestone, completed_on in retro window. Region/Audience: this project carries no Region or Audience custom field — confirmed null, not omitted.

## Slide 6
RETROSPECTIVE
Campaign Performance (Salesforce)
Campaign | Members | Responses | Resp. Rate | Leads/Opps
em_promo_src_26_q4_atv_manifesto_source | 495 | 495 | 100%* | 495 / 4
evt_webinar_dxo...Partner Master Class | — | 128 | — | 131 / 5
ev_workshop...EvolveDigital Pre-summit Meetup | 68 | 68 | 100%* | 68 / 0
evt_webinar_dc...AcquiaxDrupalAssocWebinar | — | 109 | — | 109 / 2
em_promo_Scottish Web Folk Conference_2026_q3 | 89 opened/11 clicked | 100 | — | 100 / 0
evt_ws_26_q3_all_dam workshop boston 2026 | — | 14 | — | 14 / 2
Period roll-up (all 123 campaigns created/started 09-10..09-16): 376 leads + 542 contacts (918 total) · 915 responses · 13 opportunities · 3 won · $0.000152 attributed pipeline.
*Response rate shown only where Members and Responses both trace to the same field; most rows report Responses only — see slide 19.
Source: Salesforce SOQL, Campaign WHERE CreatedDate=LAST_N_DAYS:7 OR StartDate=LAST_N_DAYS:7 (123 rows); CampaignMember GROUP BY CampaignId,Status. MOps → SFDC link: manifesto Source, EvolveDigital, and Scottish Web Folk map directly to Asana tickets completed this period.

## Slide 7
RETROSPECTIVE
SLA & Cycle Time
0 of 7
SFDC campaign builds within the
1-business-day SLA target
13.6 bd
Average cycle time (created→completed)
4.4bd excluding 2 backlog items from July
Item | Created | Completed | Cycle (bd)
SFDC Creation and List Upload - Febraban Tech 26 | 09-03 | 09-10 | 5
SFDC Campaign Creation (HS Webinar Sept 24) | 09-14 | 09-16 | 2
MAC 2026 SFDC Campaign(s) & Form | 09-09 | 09-15 | 4
Acquia TV manifesto Source - Email Campaign Build | 09-04 | 09-10 | 4
Acquia TV manifesto WaterAid - Email Campaign Build | 09-04 | 09-15 | 7
MAICON SFDC Campaigns w/ Parent (backlog) | 07-23 | 09-16 | ~38
Content Marketing World SFDC Campaign(s) & Form (backlog) | 07-23 | 09-10 | 35
Target per sla-watchdog SLA table: SFDC Campaign creation (≤5 campaigns) = 1 business day. No breach/at-risk fields exist on these tasks — cycle time computed from created_at→completed_at business days, per prior weeks' methodology (no clean submission-date field in Asana).

## Slide 8
RETROSPECTIVE
Lead Weekly Wins — Aayushi Sharma
• Shipped 3 SFDC campaign builds this week: MAC 2026, Acquia TV manifesto WaterAid, and Content Marketing World SFDC Campaign(s) & Form — all now live campaign records.
• Built and shipped the Acquia TV manifesto Source email + SFDC campaign, which is already producing results: 495 responses and 4 opportunities logged against it.
• Completed 4 email builds/promos across Drupal Canvas & Agentic Content (2 promo sends) and the DAM Workshop NYC/DC pre-event sends.
• 14 tasks completed total this period — the highest individual count on the team.

## Slide 9
RETROSPECTIVE
Team Performance Highlights
Harish Pandey
8 tasks completed — 2 SFDC campaign creations, 2 list uploads (BBDD SOLA26, BBDD BR26 - both still flagged "Waiting for Feedback" despite being checked complete), and 4 email/campaign items including the Febraban Tech 26 SFDC + list upload build.
Felipe Tencio
11 tasks completed — the team's second-highest count. Delivered 3 audience builds, the EvolveDigital Pre-summit Meetup list upload (which is already live in SFDC with 34 registered / 34 attended), the Febraban BR list upload, and the Partner Master Class webinar wrap-up.
Jennifer Schroback
No task completions logged in the [MOps] Intake board this period. Jennifer's active work this week was outside Asana: rolling out the new MOPS_score lead-scoring field (replacing account engagement score) and sharing a new Claude skill for SFDC campaign naming with the team.

## Slide 10
LOOK AHEAD
Planning Next Week
September 17 – September 27, 2026

## Slide 11
LOOK AHEAD
Upcoming Tasks by Team Member
Harish Pandey
18
Unassigned
13
Aayushi Sharma
8
Felipe Tencio
5
Jennifer Schroback
0
Total Capacity Required: 44 Tasks
Source: Asana [MOps] Intake — search_tasks, due_on 2026-09-17..2026-09-27, top-level + sub-tasks (44 total, 8 top-level + 36 sub-tasks).

## Slide 12
LOOK AHEAD
Upcoming Email Sends Next Week
Send / Campaign Name | Send Date | Region / Audience
[Scottish Web Folk] Email to Higher Ed Send | 2026-09-17 | Not tracked (no field)
September 2026 Partner Newsletter Send | 2026-09-17 | Not tracked (no field)
HS Webinar Sept 24 - Email invite 1 | 2026-09-17 | Not tracked (no field)
Webinar with Hounder and LADWP Email invite 3 | 2026-09-17 | Not tracked (no field)
DrupalCamp Italy Wrap Around Event Email 1 | 2026-09-17 | Not tracked (no field)
Partner Summer Party - Thank you Email send | 2026-09-18 | Not tracked (no field)
[DrupalCon Rotterdam] Second email send - 22nd Sept | 2026-09-22 | Not tracked (no field)
HS Webinar Sept 24 - Email invite 2 | 2026-09-23 | Not tracked (no field)
DrupalCamp Italy Wrap Around Event Email 2 | 2026-09-24 | Not tracked (no field)
AT RISK
Capacity clash: 5 of 9 upcoming sends land on the same day (09-17), all owned by Harish Pandey. No Region/Audience field exists to check for audience overlap — flagged as an owner-capacity clash, not a confirmed audience collision.
Source: Asana milestone sub-tasks, Project Type = Email(s) only | Nurture Sequences, resource_subtype=milestone, due_on 2026-09-17..2026-09-27.

## Slide 13
LOOK AHEAD
Priority Pipeline — Aayushi Sharma
No Priority field values are set on any of these tickets (custom field null across the board) — shown by due date instead of priority tier.
Task | Due
Drupal Canvas and Agentic Content: Post-Event No-Show Email | 09-17
Drupal Canvas and Agentic Content: Post-Event Attendee Email | 09-17
Drupal Canvas and Agentic Content: Webinar Email Creation | 09-17
Atlanta Tech Week 2026 Post Event Marketing Emails | 09-17
DAM Workshop DC Pre Event Marketing Emails | 09-17
Gartner IT Symposium SFDC Campaign(s) & Form (If Required) | 09-23
[Event Name] Post Event Marketing Emails | 09-24
[Event Name] Post Event Marketing Emails (DAM Workshop Boston) | 09-24

## Slide 14
LOOK AHEAD
Upcoming Strategic Priorities
Harish Pandey
18 items due — the heaviest look-ahead load on the team, 9 of them email sends (5 landing on 09-17 alone). Also carries the HS Webinar Sept 24 SFDC + email build and both DrupalCamp Italy wrap-around emails.
Felipe Tencio
5 items due, concentrated in Audiences work — 4 of the 5 open Audiences tickets in the project sit with Felipe, plus the Drupal Canvas Attendee/No-Show Report Upload.
Jennifer Schroback
No items due in this window. Open action outside Asana: the MOPS_score field rollout she announced this week asks the team to update any reports/dynamic lists referencing the old account engagement score by EOD 09-17.

## Slide 15
LOOK AHEAD
Active Sub-Projects
Sub-Category | Core Activity | Status
Email(s) only ¦ Nurture Sequences | 15 open tickets — dominant category, heavy Harish send load | 
Unclassified (null Project Type) | 10 open tickets with no Project Type set | 
Audiences | 5 open tickets, 4 with Felipe Tencio | 
IT/Integration | 4 open tickets incl. Zapier-LinkedIn (blocked 203 days) and Meta Lead Forms CAPI setup | 
SFDC Campaigns only (multiple) | 3 open tickets — fully human, no n8n coverage | 
Other | 3 open tickets | 
Form Request | 2 open tickets | 
List Upload / Webinar / Reporting / Issues / Event | 1 open ticket each | 
IN PROGRESS
AT RISK
IN PROGRESS
BLOCKED
READY
IN PROGRESS
READY
ON TRACK
Source: Asana [MOps] Intake — all 47 open top-level tickets, grouped by Project Type custom field.

## Slide 16
LOOK AHEAD
Incomplete Tickets
Ticket | Assignee | Missing Info | Priority
Zapier integration - LinkedIn | Unassigned | Waiting on direct Pardot↔LinkedIn integration; deprioritized by design since 03-02 (~203 days) | Not set
[Event Name] Pre Event Marketing Emails | Unassigned | Email copy requested from Michelle Glass, never received (~66 days); also carries a literal [Event Name] placeholder, ~48 days past its own due date | Not set
Optimize Starter upon ACP Renewal - Email Cadence | Karen Plant | Orphaned from a departed teammate; Karen asked 04-28 if it can be archived — no reply since (~142 days) | Not set
Create contact list for ICP 2026 (Platform for Drupal / Smarter Content) | Unassigned | Requester (Deepak) asked twice (02-10, 03-10) what the list is for and which system to pull from — no response (~203 days) | Not set
Source: Asana MOPS-Status custom field = Blocked / Require Information/Description / Waiting for Feedback, cross-checked against task stories for the specific block reason. Priority field is null on all 4 — a standing gap, not omitted.

## Slide 17
LOOK AHEAD
Data Hygiene & Recommendations
Flagged this period:
• 107 of 123 new campaigns (87%) show zero members 5+ business days after creation — all share CreatedDate 2026-09-10 and are entirely vccp_/demgen_ paid-media types.
• 120 of 123 new campaign names don't follow Region_Channel_Product_Description_YYYY-Qn (advisory, per campaign-naming skill) — only 3 NA_evt_ event campaigns come close.
• $0.000152 total attributed pipeline despite 3 won opportunities and 13 total opportunities — the AmountAllOpportunities/won-$ rollup looks unreliable, not that revenue is actually zero.
Recommendations:
1. Confirm with RevOps whether vccp_/demgen_ paid-media campaign types are expected to carry CampaignMembers at all — settling this for the 107 flagged campaigns prevents a false "zero-member" alarm every week this batch runs.
2. Fix the opportunity-amount rollup before next quarter's ROI review — unlocks real pipeline reporting for the 4 campaigns (Acquia TV manifesto Source, DAM Workshop Boston, DrupalAssociation webinar, Partner Master Class) that already show opportunity activity.
3. Naming convention drift is advisory, not a hard fail — flagging for Jennifer's naming-enforcement track rather than remediating unilaterally.

## Slide 18
Closing / Questions
Next Review: 2026-09-24 | Lead: Aayushi Sharma

## Slide 19
Data & Image Sources
Connectors queried (2026-09-17, this run):
• Asana — [MOps] Intake project (gid 1205660951274722). search_tasks for completed (retro window) and open/due (look-ahead window), top-level and sub-tasks, both completion states for email milestones, MOPS-Status filters for blocked/require-info/waiting tickets, get_task_stories for block reasons, get_task for created_at/completed_at on 7 SFDC-campaign-only builds.
• Salesforce — soqlQuery against Campaign (WHERE CreatedDate=LAST_N_DAYS:7 OR StartDate=LAST_N_DAYS:7, 123 rows) and CampaignMember (GROUP BY CampaignId, Status). getObjectSchema('Campaign') confirmed all fields used exist as named — no substitutions needed. Query-only, no writes.
• Jira (Atlassian MCP) — JQL project=MOPS AND updated in retro window (3 issues); direct getJiraIssue on MOPS-659156 for continuity. Connector worked on first attempt.
Gaps and known issues found this run:
• No Region or Audience custom field exists anywhere in the [MOps] Intake project — every "Not tracked" cell on slides 5/12 is a genuine field gap, not omitted data.
• Priority custom field is null on all 4 incomplete tickets (slide 16) and across most of the open board.
• Data-quality: 4+ tasks checked complete in Asana while MOPS-Status still reads an in-progress value; 2 tasks (Gartner IT Symposium pair) show MOPS-Status=Completed while still open with a future due date; the [Event Name]/[NAME]/[Webinar Name] template-placeholder bug is still live across 9+ tasks pulled this run.
• AmountAllOpportunities/won-$ rollups read as unreliable (see slide 17) — consistent with the known caveat in the pipeline-influenced-email skill.
• Google Slides upload: not attempted this run — see delivery note (8th consecutive week the inline-base64 Drive upload path can't carry a deck this size; flagged, not retried).
No numbers on this deck were invented — every figure traces to one of the three queries above.