## Slide 1
MOps Weekly Review
Team Performance, Campaign Results & Strategic Roadmap
September 3, 2026 | Project Review Meeting

## Slide 2
RETROSPECTIVE
Reviewing Last Week
Retro period: Aug 27 – Sep 2, 2026

## Slide 3
RETROSPECTIVE
Executive Summary
41
Tasks completed
3
Campaigns w/ live engagement
260
Contacts/leads reached
50%
SFDC builds within SLA
41 tasks completed in Asana [MOps] Intake this week — 30 from the core MOPS team (Aayushi 17, Harish 9, Felipe 4, Jennifer 0), plus 3 unassigned and 8 from cross-team assignees (Kim Bonilla, Nicole Ngoon) picking up auto-expanded webinar sub-tasks. Aayushi advanced 10 SFDC Campaign-only work items and closed 7 email-build/audience subtasks; Harish shipped 2 event SFDC campaigns (DrupalCamp Spain, DrupalCamp Italy) plus 2 list uploads; Felipe delivered 4 audience/reporting pulls — 2 of them against tickets still carrying the literal "[Event Name]" placeholder (see slide 17).
3 of the 65 Salesforce campaigns created or started this period show live member/response data, reaching 260 contacts+leads combined (256 responses). The other 62 show zero members — 43 of those are now 5–6 business days old, past the zero-after-5-days hygiene threshold (see slide 17). No opportunities or pipeline $ are attributed to this period's campaigns yet, which may reflect normal lag rather than a problem.
5 of 10 SFDC Campaign-only builds landed inside the 1–2 business day SLA target (50%), average cycle time 4.3 business days. No Rush/Urgent-flagged completions this week. 1 ticket remains BLOCKED (Zapier–LinkedIn integration, ~7.7 months, no stated reason) and 3 of Aayushi's look-ahead tickets are AT RISK — due this week with substantially blank intake forms (Connect 2026, DigiCol26, MAICON).
Source: Asana [MOps] Intake (search_tasks, completed_on 2026-08-27 to 2026-09-02); Salesforce Campaign/CampaignMember SOQL. Queried 2026-09-03.
3

## Slide 4
RETROSPECTIVE
Completed Tasks by Team Member
Aayushi Sharma
17
Harish Pandey
9
Felipe Tencio
4
Jennifer S.
0
Team total: 30 completed
Source: Asana [MOps] Intake, tasks completed 2026-08-27 to 2026-09-02 (includes sub-tasks and email-send milestones). +3 unassigned, +8 from cross-team assignees on auto-expanded webinar sub-tasks (Kim Bonilla 7, Nicole Ngoon 1), not shown above — grand total incl. all assignees: 41. Jennifer had no Asana completions this week; she owns the 3 no-pattern intake types.
4

## Slide 5
RETROSPECTIVE
Emails Sent Last Week
SEND / CAMPAIGN NAME | SEND DATE | REGION / AUDIENCE | OWNER
Drupal GovCon 2026 Post Event Marketing Emails | Tue, Sep 1 | Not set on the milestone (see gap note) | Aayushi
[DAM New Features Partner Webinar] Registration Email 1 | Tue, Sep 1 | Not set on the milestone (see gap note) | Aayushi
Source: Asana [MOps] Intake, completed Email-type milestone sub-tasks due 2026-08-27 to 2026-09-02. GAP: the Region/Audience field is not populated on either milestone this period — a known data gap flagged in prior weekly reviews since 2026-07-13, still open.
5

## Slide 6
RETROSPECTIVE
Campaign Performance (Salesforce)
These are the only 3 of 65 campaigns (created/started 2026-08-27 to 2026-09-02) with actual member/response data — 62 show zero members, and 43 of those are now 5–6 business days old, past the zero-after-5-days hygiene threshold (see slide 17).
CAMPAIGN | CONTACTS/LEADS | RESPONSES | RESP. RATE | OPPS / WON | PIPELINE $
em_promo_dc_26_q3_all_acquiaxdrupalassociationwebinar | 4 / 0 | 0 | 0% | 0 / 0 | $0
em_promo_dxo_26_q3_partner_DAM Updates Partner Master Class | 253 / 0 | 253 | 100% | 0 / 0 | $0
evt_webinar_dc_26_q3_all_acquiaxdrupalassociationwebinar | 1 / 2 | 3 | 100% | 0 / 0 | $0
PERIOD TOTAL (3 campaigns with any engagement) | 258 / 2 | 256 | – | 0 / 0 | $0
Source: Salesforce SOQL on Campaign (CreatedDate = LAST_N_DAYS:7 OR StartDate in retro window) and CampaignMember (GROUP BY CampaignId, Status), queried 2026-09-03. No opportunities or pipeline $ attributed to any campaign from this period yet — may reflect normal lag, not absence.
6

## Slide 7
RETROSPECTIVE
SLA & Cycle Time
No clean "submission date" field exists in Asana separate from task-creation date, so cycle time (created → completed, business days) is reported as the SLA proxy, per the sla-watchdog SOP.
SFDC Campaign-only builds (target: 1–2 business days)
– 5 of 10 completed within SLA (50%) — avg cycle time 4.3 business days.
– Fastest: "DAM Workshop NYC Email Campaign" and "[DAM New Features Partner Webinar] Email Campaign Build" (Aayushi), same-day (0 bd).
– Slowest: "Henry Stewart DAM NY 2026 SFDC Campaign(s) & Form" (10 bd, Aayushi); "[DrupalCamp Spain]" / "[DrupalCamp Italy]" SFDC Campaign and "SFDC Creation – BBDD BR Prospection" (8 bd each, Harish).
Rush / Late
– No tickets flagged "Out of SLA/Rush = Yes" among this week's completions.
Source: Asana [MOps] Intake created_at/completed_at for the 10 completed Project Type = "SFDC Campaign only (single)" tasks/sub-tasks, computed 2026-09-03. SLA target per sla-watchdog SKILL.md. Business-day math excludes weekends only (no holiday calendar).
7

## Slide 8
RETROSPECTIVE
Lead Weekly Wins — Aayushi Sharma
SFDC Campaigns & CID Work Delivered (10)
– DAM Workshop NYC Email Campaign, Drupal Canvas and Agentic Content Email Campaign Build, [DAM New Features Partner Webinar] Email Campaign Build — 3 webinar/event campaign builds this week.
– SFDC CID Requests × 3 (Source AI Cites, The Agentic Marketing Team, Vertical Velocity 2.0) — UTM/CID cleanup across paid-media flights.
– BPFD Intentsify SFDC Campaign Only, Henry Stewart DAM NY 2026 SFDC Campaign(s) & Form, "Campaign creation" — same-day to 10-day builds.
Email Sends & Builds
– 2 milestone sends delivered: Drupal GovCon 2026 Post-Event Marketing Emails; [DAM New Features Partner Webinar] Registration Email 1.
– 5 more email-build subtasks advanced: Content Marketing World Pre-Event, DrupalCamp Colorado Post-Event, [DAM New Features Partner Webinar] Registration Email Build 2, Drupal GovCon Post-Event Email Build, Drupal Canvas Email Build 01.
Source: Asana [MOps] Intake completions 2026-08-27 to 2026-09-02, assignee Aayushi Sharma.
8

## Slide 9
RETROSPECTIVE
Team Performance Highlights
🧩
Harish Pandey
• 2 event SFDC campaigns: [DrupalCamp Spain], [DrupalCamp Italy] SFDC Campaign for main event (8 bd cycle each).
• SFDC Creation – BBDD BR Prospection + SFDC List Upload – BBDD SOLA cleared (8 bd each).
• [DrupalCon Rotterdam] SFDC Campaign; Atlanta Tech Week 2026 List Upload; MOPs Add CID to Form.
📋
Felipe Tencio
• 4 audience/reporting deliverables: DAM Workshop NYC Pre-Event Audience Report; [Webinar Name] Webinar Audience Selection; 2× [Event Name] Post-Event Audience Report.
• 2 of the 4 landed against tickets still carrying the literal "[Event Name]"/"[Webinar Name]" placeholder — see Data Hygiene, slide 17.
🧭
Jennifer Schroback
• 0 Asana completions this week — she owns the 3 no-pattern types (IT/Integration, Automations|Martech, UAT); none closed this period.
• No task-count proxy captures triage/investigation work. Slack was not queried this generation run (see slide 19) — narrative context here is Asana-only.
Source: Asana [MOps] Intake completions + assignments, 2026-08-27 to 2026-09-02.
9

## Slide 10
LOOK AHEAD
Planning Next Week
Look-ahead period: Sep 3 – Sep 13, 2026

## Slide 11
LOOK AHEAD
Upcoming Tasks by Team Member
Aayushi Sharma
11
Harish Pandey
8
Felipe Tencio
7
Jennifer S.
0
Total Capacity Required: 37 Tasks
Source: Asana [MOps] Intake, open tasks due 2026-09-03 to 2026-09-13, queried 2026-09-03. 26 across the core team + 1 from Michelle Glass (non-MOPS assignee) + 10 unassigned, not shown above. Aayushi carries 11 of 26 core-team upcoming tasks (42%) — still the heaviest load, down from 55% last week.
11

## Slide 12
LOOK AHEAD
Upcoming Email Sends Next Week
⚠ Same-day capacity flag: Harish has 2 sends both due Sep 3 — DrupalCamp Italy Email 1 and Partner Summer Party London Email 3 — different events, worth confirming audiences don't overlap.
SEND / CAMPAIGN NAME | SEND DATE | REGION / AUDIENCE | OWNER
[DAM New Features Partner Webinar] Registration Email Send 2 | Thu, Sep 3 | Not set on the milestone | Aayushi
DrupalCamp Italy Wrap Around Event Email 1 | Thu, Sep 3 ⚠ | Not set on the milestone | Harish
Partner Summer Party – London Email 3 send | Thu, Sep 3 ⚠ | Not set on the milestone | Harish
Drupal Canvas and Agentic Content: Email 2 Promo | Tue, Sep 8 | Not set on the milestone | Aayushi
[DAM New Features Partner Webinar] Registration Email Send 3 | Wed, Sep 9 | Not set on the milestone | Aayushi
Webinar with Hounder and LADWP Email invite 2 | Thu, Sep 10 | Not set on the milestone | Harish
Partner Summer Party – London Email 4 send | Fri, Sep 11 | Not set on the milestone | Harish
Source: Asana [MOps] Intake, incomplete Email-type milestone sub-tasks due 2026-09-03 to 2026-09-13. GAP: Region/Audience not populated on any milestone (same gap as slide 5).
12

## Slide 13
LOOK AHEAD
Priority Pipeline — Aayushi Sharma
11 of 26 core-team upcoming tasks (42%) — still the heaviest load on the team, though down from 55% last week.
Due Sep 3 (today)
– Connect 2026 SFDC Campaign — AT RISK: Campaign Name blank, rest of form complete, due today.
– [DAM New Features Partner Webinar] Registration Email Build 3, Registration Email Send 2, [DAM Workshop Boston] Email Send – 03 — also due today.
Due Sep 4
– DigiCol26 SFDC Campaign(s) — AT RISK: entire form blank except a partial notes string, due tomorrow.
– MAICON SFDC Campaign(s) & Form (If Required) — AT RISK: entire form blank, due tomorrow.
– Content Marketing World SFDC Campaign(s) & Form (If Required).
Due Sep 8–12
– Drupal Canvas and Agentic Content: Email 2 Promo (Sep 8); [DAM New Features Partner Webinar] Registration Email Send 3 (Sep 9).
– Churn customer campaign – Dynamic Pardot sequence (Sep 10); Henry Stewart DAM NY 2026 Pre-Event Marketing Emails (Sep 12).
Source: Asana [MOps] Intake, open tasks assigned to Aayushi Sharma due 2026-09-03 to 2026-09-13.
13

## Slide 14
LOOK AHEAD
Upcoming Strategic Priorities
🧩
Harish Pandey
• 4 email sends queued incl. the Sep 3 same-day pair (DrupalCamp Italy + Partner Summer Party London).
• 2 new-event SFDC campaigns queued: [FOST Paris] SFDC Campaigns, [OnDAM Paris] SFDC Campaign — both due Sep 8.
• DAM New Features Partner Webinar (Sep 10); Upload list into SF (Sep 7).
📋
Felipe Tencio
• 7 audience/report pulls due Sep 3–12: DrupalCamp Italy Wrap Around Event Audience (Sep 3).
• 5 of the remaining 6 are literal "[Event Name]" Post/Pre-Event Audience Report placeholder tickets (Sep 8 ×3, Sep 11 ×2, Sep 12 ×1) — blocked until the underlying template bug is traced (see slide 17).
❓
Unassigned (10 tasks)
• 2 SFDC list uploads (BBDD BR26, BBDD SOLA26, Sep 8); MOPs Add CID to Form (Sep 12).
• 4 webinar-mechanics subtasks due Sep 9–12 (Zoom edit, stakeholder copy review, social copy/scheduling, landing page + form).
• EvolveDigital Pre-summit Meetup, [Webinar Name] Webinar Banner Request — both due Sep 3.
Source: Asana [MOps] Intake, open tasks due 2026-09-03 to 2026-09-13, queried 2026-09-03.
14

## Slide 15
LOOK AHEAD
Active Sub-Projects
SUB-CATEGORY | CORE ACTIVITY THIS PERIOD | STATUS
SFDC & UTM Campaigns | 13 work items completed (10 single + 3 multiple-campaign); 6 more queued (Connect 2026, DigiCol26, MAICON, Content Marketing World, FOST Paris, OnDAM Paris) — 3 of the queued items AT RISK on blank/near-blank forms. | AT RISK
Email Requests | 8 email-build subtasks + 2 milestone sends completed (260 contacts/leads reached); 11 more queued incl. 7 milestone sends, with a Sep 3 same-day pair. | IN PROGRESS
Webinar Requests | No pure Webinar Request-type tickets closed this period; 2 queued for look-ahead — webinar work continues to run under Email/SFDC types instead. | READY
List Uploads | 4 completed (BBDD SOLA, Atlanta Tech Week, Upload list into SF, +1); 1 queued (unassigned) plus 2 more list uploads due Sep 8. | ON TRACK
Audiences / Reporting | 5 completed (Felipe); 7 queued — 5 of the 7 are literal "[Event Name]" placeholder tickets (see slide 17). | IN PROGRESS
Source: Asana [MOps] Intake Project Type field, retro + look-ahead windows, queried 2026-09-03.
15

## Slide 16
LOOK AHEAD
Incomplete Tickets
TICKET | ASSIGNEE | MISSING INFO | PRIORITY
Zapier integration – LinkedIn | Unassigned | BLOCKED ~7.7 months (created Jan 12) — no stated blocker in Notes | BLOCKED
Connect 2026 SFDC Campaign | Aayushi | Campaign Name blank; rest of form complete; due today | AT RISK
DigiCol26 SFDC Campaign(s) | Aayushi | Entire form blank except a partial notes string; due tomorrow | AT RISK
MAICON SFDC Campaign(s) & Form | Aayushi | Entire form blank; due tomorrow | AT RISK
[Event Name] Pre Event Marketing Emails | Unassigned | Require Info/Description, ~2.1 months open (created Jul 1), no stated blocker | NEEDS INFO
Create contact list – #1 Platform for Drupal ICP 2026 | Unassigned | Waiting for Feedback, ~7.1 months open (created Feb 2) | NEEDS INFO
Optimize Starter upon ACP Renewal – Email Cadence | Karen Plant | Require Info, ~12.9 months open (created Aug 2025) — awaiting ACP-renewal report from Nate | NEEDS INFO
Source: Asana [MOps] Intake, MOPS-Status = Blocked (1) or Require Information/Description (2) or Waiting for Feedback (1) among open top-level tickets, + 3 AT RISK items surfaced from the Priority Pipeline (slide 13), queried 2026-09-03. "Missing Info" quoted from each task's own Notes/form fields.
16

## Slide 17
LOOK AHEAD
Data Hygiene & Recommendations
Flagged this period
– Naming drift: none of the 65 campaigns created/started this period follow the Region_Channel_Product_Description_YYYY-Qn convention — legacy patterns in active use (em_promo_..., evt_webinar_..., demgen_..., Social_WW_src_..., Partner_cloud-platform-trial_..., Content_Chaos_Quiz_...). Advisory, not a hard fail.
– Zero-member aging: 43 of the 65 new campaigns are now 5–6 business days old with zero Contacts/Leads — past the zero-after-5-days threshold. Mostly paid-media flights (EDU/NGO/FinServ/Source AI Cites/Agentic Marketing/Content Chaos Quiz, 41 campaigns) plus 2 named builds (Henry Stewart DAM NY 2026, BPFD Intentsify Display).
– "[Event Name]"/"[Webinar Name]" placeholder bug persists: 2 completed + 5 queued audience-report tickets carry a literal placeholder instead of a real name — same live substitution bug the intake-dispatch routine has flagged.
– Jira MOPS-659156 (Click-ID fields not flowing Campaign Member → Lead/Contact) remains Need Info/Blocked, assigned to Jennifer, unchanged since Aug 25 — recurring across multiple weekly reviews.
– Email-send milestones (2 sent + 7 upcoming = 9 checked) still carry no Region/Audience value — gap open since 2026-07-13.
Recommendations
– 1. Check in on the 43 zero-member campaigns now past the 5-day threshold — confirm which are paused paid-media flights (by design) vs. stalled builds; protects response-rate reporting for the whole Q3 cohort.
– 2. Fix the 3 AT RISK SFDC campaign forms before their Sep 3–4 due dates — Connect 2026 needs only a Campaign Name; DigiCol26 and MAICON need the requester to resubmit a complete form.
– 3. Trace the "[Event Name]" placeholder bug in the audience-report template — it has now hit 7 tickets across 2 consecutive weekly reviews (2 completed this period, 5 queued next), each one blocking Felipe from starting real work until manually renamed.
Source: Salesforce Campaign naming/member audit (this period's 65 campaigns); Asana MOPS-Status field; Jira MOPS-659156; Asana email-milestone custom fields. Queried 2026-09-03.
17

## Slide 18
Questions?
Thank you
Next Review: September 10, 2026 | Lead: Aayushi Sharma

## Slide 19
APPENDIX
Data & Image Sources
Connectors queried (2026-09-03, this run)
– Asana MCP — [MOps] Intake project (gid 1205660951274722): search_tasks for retro completions (top-level + sub-tasks + milestones), look-ahead due tasks, open flagged tickets (MOPS-Status), Email-type milestones sent + upcoming.
– Salesforce MCP — soqlQuery on Campaign (CreatedDate = LAST_N_DAYS:7 OR StartDate in retro window) and CampaignMember (GROUP BY CampaignId, Status) for the 3 campaigns with live data.
– Atlassian (Jira) MCP — searchJiraIssuesUsingJql, project = MOPS, updated since 2026-08-27; plus a direct lookup of MOPS-659156 for continuity with prior reviews.
– Slack — NOT queried this generation run (explicitly out of scope for this pass; the Slack post and any additional narrative context happens separately, driven by the parent session).
Known gaps — stated plainly, not guessed around
– No clean "submission date" field distinct from Asana task-creation date — cycle time (created→completed) used as the SLA proxy throughout, per sla-watchdog SOP.
– Region/Audience not populated on any Email-type milestone sub-task checked this period (9 of 9: 2 sent + 7 upcoming).
– Google Slides upload not attempted this run — known base64 output-token wall, confirmed 6 consecutive weeks (2026-07-23, 07-30, 08-13, 08-20, 08-27, 09-03).
Images
– No external images used — all charts/tables are native PowerPoint shapes built from the queried data above; no attribution required.
Deck built locally: outputs/weekly-review/MOps_Weekly_Review_2026-09-03.pptx