## Slide 1
MOps Weekly Review
Team Performance, Campaign Results & Strategic Roadmap
October 29, 2026 | Project Review Meeting

## Slide 2
RETROSPECTIVE
Reviewing Last Week
October 22 – 28, 2026

## Slide 3
RETROSPECTIVE
Executive Summary
61
tasks completed (8 top-level requests + 53 sub-tasks)
Result 1
61 tasks shipped — 8 top-level requests + 53 sub-tasks, the largest completion count logged this quarter
Result 2
25 Salesforce campaigns created/launched in-window, reaching 7,657 contacts+leads and logging $69.4K pipeline across 13 opportunities
Result 3
Two of the board's oldest open tickets — the "[Event Name]" placeholder Pre/Post-Event Marketing Email requests, open since July 1 — finally closed this week after ~85 business days each
A strong completion week driven largely by clearing backlog: the team closed both long-stalled "[Event Name]" placeholder tickets and two SFDC campaigns tied to months-old initiatives (DigiCol26, Drupal 12 Holiday Party). Offsetting that, the Meta Lead Forms integration remains 41 days past due with no escalation — see slide 16.
Source: Asana [MOps] Intake (project 1205660951274722), get_tasks completed_since=2026-10-22, 3 pages; Salesforce Campaign SOQL — queried 2026-10-29.

## Slide 4
RETROSPECTIVE
Completed Tasks by Team Member
Aayushi Sharma
24
Harish Pandey
22
Felipe Tencio
13
Jennifer S.
1
Unassigned
1
Source: Asana [MOps] Intake, completed_at 2026-10-22–10-28 (61 tasks: 8 top-level + 53 sub-tasks). Queried 2026-10-29.

## Slide 5
RETROSPECTIVE
Emails Sent Last Week
Send Date | Send / Campaign Name | Owner | Region/Audience
Oct 22 | Acquia Festive Party, Paris — Email Invite 1 | Harish Pandey | Not populated
Oct 22 | Dries Prospects + Customer Campaign — Prospect Email Copy | Felipe Tencio | Not populated
Oct 22 | Atlanta Marketing Leadership Dinner — Email Promo 2 | Aayushi Sharma | Not populated
Oct 23 | Email to all partners about PHP security issues | Harish Pandey | Not populated
Oct 23 | DAM New Features Partner Webinar — Post-Webinar No-Show Email | Aayushi Sharma | Not populated
Oct 23 | DAM New Features Partner Webinar — Post-Webinar Attendee Email | Aayushi Sharma | Not populated
Oct 23 | DAM Workshop DC — Email Invite 02 | Aayushi Sharma | Not populated
Oct 26 | October 2026 Partner Newsletter | Harish Pandey | Not populated
Oct 27 | [OnDAM Paris] Pre-Event Email | Harish Pandey | Not populated
Oct 27 | DAM Workshop San Francisco 2026 — Email Promo 01 | Aayushi Sharma | Not populated
Oct 27 | DAM Workshop DC — Email Invite 03 | Aayushi Sharma | Not populated
Oct 28 | Acquia Festive Party (The Cube, London) — Email 2 | Harish Pandey | Not populated
Oct 28 | LinkedIn Live Series with Capgemini — Promo Send | Harish Pandey | Not populated
Oct 28 | Dries Prospects + Customer Campaign — Customer Email Copy | Felipe Tencio | Not populated
Oct 28 | The Gathering, Banff — Post-Event Email | Aayushi Sharma | Not populated
15 email-milestone sub-tasks completed, due 2026-10-22–10-28. Gap: Region/Audience custom field is unpopulated on every email milestone — a known gap carried from prior weeks, not inferred. Source: Asana search_tasks, resource_subtype=milestone.

## Slide 6
RETROSPECTIVE
Campaign Performance (Salesforce)
Campaign | Type | Members | Responses | Resp. Rate | Opps/Pipeline
em_promo_connect_2026_Q4 | Email | 0 | 0 | 0 | 0/0
em_promo_MAICON_2026_Q4 | Email | 0 | 0 | 0 | 0/0
em_promo_Gartner_IT_Symposium_2026_Q4 | Email | 0 | 0 | 0 | 0/0
em_promo_dc_q4_26_customers_driesemailpromo | Email | 41 | 41 | 100% | 0/0
em_promo_the_gathering_banff_2026_q4 | Email | 70 | 70 | 100% | 0/0
evt_ts_giw_federal_apj_dc_2026-q4 | Event | 36 | 36 | 100% | 0/0
em_Nurture_BPFD-MultiSite_Consolidation_2026_Q4 | Email | 0 | 0 | 0 | 0/0
NA_EVT_...Banff_Acquia_Session_Scans_2026_Q4 | Event | 0 | 0 | 0 | 0/0
NA_EVT_...Banff_Aura_Booth_Scans_2026_Q4 | Event | 484 | 482 | 99.6% | 2/0
NA_EVT_...Banff_2026_Q4 | Event | 0 | 0 | 0 | 0/0
em_promo_DAM Workshop San Francisco_2026_q4 | Email | 146 | 146 | 100% | 1/$17
em_promo_dxp_DigiCol26_post_event_2026_Q4 | Email | 0 | 0 | 0 | 0/0
NA_td_dxp_DigiCol26_Registered_2026_Q4 | Event | 236 | 236 | 100% | 1/$3,941
em_promo_linkedin-agentic-era-capgemini_cc_2026_q4 | Email | 4,350 | 4350 | 100% | 2/$57,186
evt_td_dc_partner_connect_q4_2026 | Event | 56 | 56 | 100% | 0/0
evt_webinar_linkedin-atomic-marketing-org-q4_2026 | Event | 1 | 1 | 100% | 0/0
evt_webinar_linkedin-shortlisted-machine-q4_2026 | Event | 1 | 1 | 100% | 0/0
evt_webinar_linkedin-ai-hype-ai-proof-q4_2026 | Event | 2 | 2 | 100% | 0/0
evt_webinar_linkedin-agentic-era-capgemini-q4_2026 | Event | 2 | 2 | 100% | 0/0
em_promo_partners_php_security_issues_dc_2026_q4 | Email | 1,119 | 1119 | 100% | 3/$1,624
evt_webinar_drupalcloud_26_q4...webinar | Zoom Webinar | 0 | 0 | 0 | 0/0
em_nl_october_partner_newsletter_ac_2026_q4 | Email | 937 | 937 | 100% | 3/$6,667
em_promo_ondam_paris_emea_cc_2026_q4 | Email | 87 | 87 | 100% | 0/0
evt_webinar_Q4_SHARPE_26 | Zoom Webinar | 89 | 84 | 94.4% | 1/0
evt_conference_dc_DrupalCamp Italy_2026_q4 | Event | 0 | 0 | 0 | 0/0
Roll-up: 25 campaigns · 7,657 members (1,156 leads + 6,501 contacts) · 7,650 responses · 2 converted leads · 13 opportunities · $69,434 pipeline. Source: SOQL on Campaign WHERE CreatedDate=LAST_N_DAYS:7 OR StartDate=LAST_N_DAYS:7, queried 2026-10-29.

## Slide 7
RETROSPECTIVE
SLA & Cycle Time
50%
within SLA (2 of 4 scored)
40.5 bd
avg cycle time among scored (n=4)
4 / 10
top-level completions with a clean SLA-table match
Ticket | SLA Type | Cycle Time | Result
SFDC List Upload — BBDD BR 2 | List Upload (3–7 bd) | 3 bd | ON TRACK
SFDC List Upload — BBDD SOLA 2 | List Upload (3–7 bd) | 3 bd | ON TRACK
DigiCol26 SFDC Campaign(s) | SFDC Campaign, single (1 bd) | 93 bd | AT RISK
Drupal 12 Holiday Party SFDC Campaign(s) | SFDC Campaign, single (1 bd) | 63 bd | AT RISK
Caveat: the two SFDC-campaign breaches are measured from sub-task creation to completion; both sub-tasks sat under months-old parent initiatives (created June/July), so the cycle time likely reflects the parent project's kickoff date rather than when the campaign-creation ask itself became actionable — flagged, not corrected for.
Rush/Late: Meta Lead Forms to Salesforce integration (Jennifer Schroback) — Priority Urgent, due 2026-09-18, now 41 days overdue, MOPS-Status still "Assigned" — never routed through the Rush/Urgent → VP/Director escalation path per SOP.
6 of 10 top-level completions (Email/Nurture x2, null Project Type x3, Webinar Request x1) have no clean SLA-table match or need a different anchor (live-date) — excluded from scoring, not silently passed.

## Slide 8
RETROSPECTIVE
Lead Weekly Wins — Aayushi Sharma
Win 1
Closed both long-stalled "[Event Name]" placeholder tickets (Pre- and Post-Event Marketing Emails), open since July 1 — clearing two of the board's oldest items after ~85 business days each.
Win 2
Landed 2 Salesforce campaigns tied to months-old initiatives: DigiCol26 (Digital Collegium) and Drupal 12 US Holiday Party.
Win 3
Carried 24 of the team's 61 completions this week — the largest individual share — while also owning 30 of 56 look-ahead tasks for next period.
Source: Asana [MOps] Intake, assignee=Aayushi Sharma, completed_at 2026-10-22–10-28.

## Slide 9
RETROSPECTIVE
Team Performance Highlights
Harish Pandey
22 completions this week.
Shipped October 2026 Partner Newsletter and closed DAM New Features Partner Webinar.
Cleared a stale duplicate ticket ("[Duplicate] Acquia Festive Party 2026 - Paris HTMLs").
Felipe Tencio
13 completions this week.
Kept audience-report and prospect/customer email-copy work moving for the Dries and DigiCol26 post-event streams.
Jennifer Schroback
1 completion (Content Marketing World List Upload).
Still owns the Meta Lead Forms integration — 41 days overdue, Rush/Urgent, unescalated.
Also owns "Add Source & Medium to paid social leads" — 27 days overdue.
Source: Asana [MOps] Intake, assignee-filtered completions and open-ticket status as of 2026-10-29.

## Slide 10
LOOK AHEAD
Planning Next Week
October 29 – November 8, 2026

## Slide 11
LOOK AHEAD
Upcoming Tasks by Team Member
Aayushi Sharma
30
Harish Pandey
11
Unassigned
7
Felipe Tencio
6
Kathy Kelleher
1
Jennifer S.
1
Total Capacity Required: 56 Tasks
"Kathy Kelleher" is not on the canonical 5-person MOPS roster (context/team.md) — flagged, not corrected. Source: Asana search_tasks, due 2026-10-29–11-08, completed=false.

## Slide 12
LOOK AHEAD
Upcoming Email Sends Next Week
Send Date | Send / Campaign Name | Owner | Clash Flag
Oct 29 | [NAME] Post-Webinar Attendee Email | Aayushi Sharma | CLASH — 3 sends
Oct 29 | Connect 2026 — Post-Event Marketing Email | Aayushi Sharma | CLASH — 3 sends
Oct 29 | [NAME] Post-Webinar No-Show Email | Aayushi Sharma | CLASH — 3 sends
Oct 29 | GAIN Interact Event 2026 — HTMLs Email 2 | Harish Pandey | Same-day, diff. owner
Oct 30 | Email A1: Awareness | Aayushi Sharma | —
Nov 2 | Atlanta Marketing Leadership Dinner — Email Promo 3 | Aayushi Sharma | Same-day as Pare & Co.
Nov 2 | Webinar with Pare & Co. — Email 2 | Harish Pandey | Same-day as Atlanta Dinner
Nov 3 | Q4'26 Acquia x Drupal Association Webinar — Email 1 Promo | Aayushi Sharma | Same-day, diff. owner
Nov 3 | [Barcelona CUG] Follow-up (plain text) | Harish Pandey | Same-day, diff. owner
Nov 5 | [Engage 2027] Save the Date Email | Harish Pandey | Same-day, diff. subject
Nov 5 | Acquia Festive Party, Paris — Email Invite 2 | Harish Pandey | Same-day, diff. subject
11 upcoming email milestones due 2026-10-29–11-05. Flag: Oct 29 has 4 sends same day — 3 owned by Aayushi Sharma (capacity clash, audience not populated to confirm overlap). Region/Audience field remains unpopulated — same known gap as slide 5.

## Slide 13
LOOK AHEAD
Priority Pipeline — Aayushi Sharma
98% (55 of 56) of look-ahead tickets have no Priority value set — the field remains unusable as a prioritization signal.
By Project Type (look-ahead)
Email(s)/Nurture: 24
Null Project Type: 20
List Upload: 3 · Audiences: 3
SFDC Campaign (single): 2 · Form: 2
Webinar: 1 · Other: 1
Known capacity risk
Aayushi owns 30 of 56 (54%) of next period's load.
4 email sends land on Oct 29 alone, 3 of them hers.
No Rush/Urgent tickets detected in this window.
Source: Asana search_tasks custom_fields.Priority, due 2026-10-29–11-08. Consistent with the ~95%+ null-Priority gap reported in prior weeks.

## Slide 14
LOOK AHEAD
Upcoming Strategic Priorities
Harish Pandey
11 tasks due, mostly email-milestone sends (Pare & Co., Barcelona CUG, Engage 2027, Acquia Festive Party Paris).
Felipe Tencio
6 tasks due — continued audience/list-pull work across open Audiences tickets.
Jennifer Schroback
1 task due next period, on top of 2 already-overdue top-level tickets carried from this week.
Source: Asana search_tasks, due 2026-10-29–11-08, by assignee.

## Slide 15
LOOK AHEAD
Active Sub-Projects
Sub-Category | Core Activity | Status
Email Requests | 26 completed this week · 24 due next period | ON TRACK
List Uploads | 15 completed this week · 3 due next period | ON TRACK
SFDC Campaigns (single) | 6 completed this week · 2 due next period | ON TRACK
Audiences | 4 completed this week · 3 due next period | ON TRACK
Webinar Requests | 1 completed this week · 1 due next period | ON TRACK
IT/Integration | 0 completed this week · 4 open (Meta Lead Forms overdue, Zapier-LinkedIn duplicated/blocked) | AT RISK
Source: Asana [MOps] Intake, Project Type field, this week's completions + look-ahead window.

## Slide 16
LOOK AHEAD
Incomplete Tickets
Ticket | Assignee | Missing Info / Blocker | Priority
Meta Lead Forms to SF Integration | Jennifer Schroback | Overdue 41 days (due 9/18); no notes on blocker; never escalated per Rush/Urgent SOP | URGENT
Zapier integration - LinkedIn (dup. #1) | Unassigned | Status Blocked; no notes documenting what's missing | HIGH
Zapier integration - LinkedIn (dup. #2) | Jennifer Schroback | Duplicate of #1, In Progress — same work tracked under 2 owners/statuses | HIGH
EMEA - GLAM/BASE campaign, Behaviour score<50 | Felipe Tencio | Waiting for Feedback — test-email/preview approval, overdue since 10/21 | MEDIUM
Add Source & Medium to paid social leads (SF) | Jennifer Schroback | Overdue 27 days (due 10/2); no notes on blocker | MEDIUM
All_Email_All_AI Web Building Assistant Demo | Unassigned | Overdue 99 days (due 7/22); unassigned and stale | MEDIUM
Sharp Webinar | Shannon Bystock* | Overdue 7 days (due 10/22); no notes on blocker | LOW
*Shannon Bystock is not on the canonical 5-person MOPS roster — flagged, not corrected. "Priority" column reflects this report's own urgency read (age × stated Rush/Urgent flag), not the mostly-null Asana Priority field. Missing-info text is taken from ticket Notes/MOPS-Status only — never invented.

## Slide 17
LOOK AHEAD
Data Hygiene & Recommendations
Flagged this period
Naming convention: 0 of 25 campaigns this window match Region_Channel_Product_Description_YYYY-Qn exactly; 3 use a close "NA_EVT_..." variant (Region+Channel present, no clear Product segment); the remaining 22 use a third, undocumented "em_/evt_..." lowercase-prefix scheme.
Zero-member campaigns: 9 of 25 show 0 members, but only 1 ("evt_conference_dc_DrupalCamp Italy_2026_q4", created 2026-08-24) is 5+ business days old — the rest were created in the last 1–7 days and are expected to still be at zero.
Type/Status/StartDate completeness: all 25 campaigns have Type, Status and StartDate populated — no blanks this window.
Recommendations for next period
Escalate the Meta Lead Forms integration (41 days overdue, Priority Urgent, still unassigned-to-escalation) through the Rush/Urgent → VP/Director path — unblocks accurate paid-social-to-SF attribution.
Merge the 2 duplicate Zapier-LinkedIn integration tickets onto one owner/status — stops the same work being tracked (and reported) twice.
Align the 22 of 25 campaigns on the alternate "em_/evt_" naming scheme to the documented convention — fixes reporting/attribution consistency for this quarter's full 25-campaign cohort.
Naming convention per .claude/skills/campaign-naming/SKILL.md (Region_Channel_Product_Description_YYYY-Qn). Flagged gently — naming guidance is advisory, not a hard fail.

## Slide 18
Questions?
Next Review: November 5, 2026 | Lead: Aayushi Sharma

## Slide 19
APPENDIX
Data & Image Sources
Connectors queried
Asana — project [MOPs] Intake (gid 1205660951274722). get_project (counts); get_tasks completed_since=2026-10-22T00:00:00Z, 3 pages, 167 total records, 61 completed-in-window; search_tasks for open top-level (parent=null, completed=false, 57 records), look-ahead due 2026-10-29–11-08 (59 raw → 56 after date-cutoff filter), and resource_subtype=milestone for sent (15) and upcoming (11) email sends. Queried 2026-10-29 ~14:42–14:55 UTC.
Salesforce — Campaign SOQL: SELECT ... WHERE CreatedDate = LAST_N_DAYS:7 OR StartDate = LAST_N_DAYS:7 (25 records, all fields populated). Queried 2026-10-29.
Jira (Atlassian cloud "acquia") — JQL project = MOPS AND updated >= -7d: 0 issues returned this window — no MOPS-linked Jira activity to report. Queried 2026-10-29.
Pardot — no MCP connector; not queried directly (Salesforce Campaign/CampaignMember rollups used as the sync target, per standing project convention).
Gaps & caveats (stated, not guessed)
No Region/Audience data on any email milestone (slides 5, 12) — custom field unpopulated, same gap as every prior week.
95%+ of open/look-ahead tickets carry a null Priority value — field remains unusable as a prioritization signal (slide 13).
The blank-name "Blocked" ticket flagged in prior weeks (gid 1218827173882954) returned "no access" this run (likely deleted) — cannot confirm its resolution, not guessed.
"Kathy Kelleher" and "Shannon Bystock" appear as assignees but are not on the 5-person canonical MOPS roster in context/team.md — flagged, not corrected or omitted.
Google Slides upload not attempted this run — see delivery note (14th consecutive week the base64 payload exceeds the tool's single-call output budget).
No images used in this deck — all visuals are native PowerPoint shapes built with python-pptx.