## Slide 1
MOps Weekly Review
Team Performance, Campaign Results & Strategic Roadmap
August 20, 2026 | Project Review Meeting

## Slide 2
RETROSPECTIVE
Reviewing Last Week
August 13 – 19, 2026

## Slide 3
RETROSPECTIVE
Executive Summary
37
tasks completed
12
SFDC campaigns created
1,720
members reached
$31.7K
email-sourced pipeline
Headline result
The "Webinar with Hounder & LADWP" promo email reached 1,544 contacts and drove 9 opportunities / $32,965 in pipeline — the standout return of the week.
Throughput
37 tasks completed across the team; Harish led on email/webinar sends (12), Aayushi on SFDC campaign + Boston DAM email builds (7).
Watch items
2 tickets BLOCKED / needs-info (Zapier–LinkedIn integration; a literal [Event Name] placeholder email ticket). Jira MOPS-659156 (paid click-ID attribution) sits Need-Info/Blocked. Campaign naming continues to drift from the documented convention (11 of 12 new campaigns).
Source: Asana [MOps] Intake (37 completions Aug 13–19) + Salesforce Campaign SOQL. Queried 2026-08-20.

## Slide 4
RETROSPECTIVE
Completed Tasks by Team Member
Harish Pandey
12
Aayushi Sharma
7
Felipe Tencio
6
Jennifer Schroback
3
Team total: 37 tasks completed
Additional contributors: Kim Bonilla 7 (DrupalCon Rotterdam webinar-planning sub-tasks) · 2 unassigned closures. Team total = 37.
Source: Asana [MOps] Intake, tasks completed Aug 13–19 2026. Core MOPS team shown.

## Slide 5
RETROSPECTIVE
Emails Sent Last Week
SEND / CAMPAIGN
SEND DATE
OWNER
REGION / AUDIENCE
DAM Workshop Boston — Email Send 01
Aug 13
Aayushi
US / DAM ICP
Partner Summer Party London — Email 2
Aug 13
Harish
EMEA / Partners
LATAM Webinar AIContent BR — Send 3
Aug 14
Harish
LATAM / Brasil
Webinar AIContent ES — Send 3
Aug 14
Harish
LATAM / Spanish
Webinar w/ Hounder & LADWP — Email 1
Aug 14
Harish
US / Public Sector
DAM Workshop Boston — Email Send 02
Aug 18
Aayushi
US / DAM ICP
DrupalCon Rotterdam Partner Summit — Email 1
Aug 18
Harish
EMEA / Partners
Source: Asana Email-type milestone sub-tasks, completed with due dates Aug 13–19 2026. Region/audience inferred from send name (Asana Region field is null on milestones).

## Slide 6
RETROSPECTIVE
Campaign Performance (Salesforce)
CAMPAIGN
MEMBERS
RESPONSES
RESP. RATE
OPPS
PIPELINE $
em_promo_webinar Hounder & LADWP
1,545
1,545
100%
9
$32,965
em_promo_dam workshop boston 2026
175
175
100%
3
-$1,227
ev_workshop_dam_ DAM Workshop NYC
0
0
—
0
$0
ev_td_dxp_ Vass CL Tradeshow
0
0
—
0
$0
evt_webinar_ DAM Updates Partner Class
0
0
—
0
$0
+ 7 more created (0 members — just built)
—
—
—
—
—
PERIOD ROLL-UP
1,720
1,720
~100%
12
$31,738
Source: Salesforce Campaign SOQL, CreatedDate or StartDate = last 7 days. Queried 2026-08-20. Response rate = NumberOfResponses / members. Negative pipeline on Boston campaign is a data anomaly — flagged on Data Hygiene.

## Slide 7
RETROSPECTIVE
SLA & Cycle Time
15 bd
Median cycle time
intake → completion, all 37
19%
Closed within 5 bd
fresh tickets closed fast
N/A
% within SLA
no per-type SLA field in Asana
Reading the number
This was a backlog-cleanup week: several long-open tickets were closed, inflating median cycle time. The oldest closure had been open 319 business days (a form-automation ticket open since May 2025). Fresh, in-period tickets closed quickly.
Rush / late
No Rush/Urgent SLA breaches surfaced in the retro window. Asana has no day-based SLA field, so a true "% within SLA" can't be computed here — see sla-watchdog for the per-type clock. Reported cycle time is intake (created) → completion in business days.
Source: Asana created_at → completed_at across 37 retro completions. SLA table lives in sla-watchdog skill, not this deck.

## Slide 8
RETROSPECTIVE
Lead Weekly Wins — Aayushi (Team Lead)
Campaign delivery
• Created 3 SFDC campaigns (Fintech MX, Havas CL Tradeshow, DAM Workshop DC) + form scaffolding.
• Built and sent both DAM Workshop Boston pre-event emails (Send 01 Aug 13, Send 02 Aug 18).
Process
• Ran the Thursday stakeholder call walking unassigned/urgent tickets and the send calendar.
Impact
• DAM Workshop Boston promo already showing 175 engaged members and 3 opportunities in Salesforce.
Source: Asana completions Aug 13–19; Salesforce campaign rollups.

## Slide 9
RETROSPECTIVE
Team Performance Highlights
Harish Pandey
Email & Webinar Sends
• 12 completions — the week's throughput leader.
• 5 webinar/nurture email sends across LATAM, EMEA & US.
• 2 SF list uploads (LA Gov Summit, CX Summit CO).
Felipe Tencio
Audiences & Lists
• 6 audience/list deliverables completed.
• Built DAM ICP prospect+customer contact lists.
• DrupalCamp Italy + Open Source AI Meet Up audiences.
Jennifer Schroback
Manager / No-Pattern
• Closed 3 long-open form & automation tickets.
• Owns the no-repeatable-shape intake types.
• Cleared the 319-day form-automation backlog item.
Source: Asana completions Aug 13–19 2026.

## Slide 10
LOOK AHEAD
Planning Next Week
August 20 – 30, 2026

## Slide 11
LOOK AHEAD
Upcoming Tasks by Team Member
Aayushi Sharma
11
Harish Pandey
10
Felipe Tencio
8
Nick Stalford
1
Unassigned
8
Total Capacity Required: 38 Tasks
8 of 38 upcoming tasks are unassigned — assign before the load-balancing gap widens.
Source: Asana [MOps] Intake, open tasks due Aug 20–30 2026.

## Slide 12
LOOK AHEAD
Upcoming Email Sends Next Week
SEND / CAMPAIGN
SEND DATE
OWNER
REGION / AUDIENCE
August 2026 Partner Newsletter
Aug 20
Harish
Global / Partners
Open Source AI Meet Up — Email send
Aug 20
Harish
Global / Prospects
[NAME] Registration Email 1 ← placeholder
Aug 20
Aayushi
TBD
DrupalCon Rotterdam — First email send
Aug 25
Harish
EMEA / Attendees
Three sends land Aug 20 — audiences differ (partner list / meetup / registration), so no audience clash, but Harish owns 2 of the 3. One send name is still a literal [NAME] placeholder — resolve before send.
Source: Asana Email-type milestone sub-tasks, incomplete, due Aug 20–30 2026.

## Slide 13
LOOK AHEAD
Priority Pipeline — Aayushi (Team Lead)
Now (this week)
• 5 SFDC campaigns due Aug 26–27 (Content Marketing World, MAICON, Gartner IT Symposium, Henry Stewart DAM NY, + Content Chaos Quiz live).
• Registration email series ([NAME] Emails 1 & 2) — resolve placeholder naming first.
Scheduled
• Churn customer campaign — dynamic Pardot sequence (Aug 26).
• Drupal GovCon & Atlanta Tech Week post-event marketing emails.
Risk
• Aayushi carries the highest look-ahead load (11 tasks) — watch for concentration.
Source: Asana open tasks due Aug 20–30 2026.

## Slide 14
LOOK AHEAD
Upcoming Strategic Priorities
Harish Pandey
Sends & Campaigns
• Partner Newsletter + Open Source AI Meet Up sends (Aug 20).
• DrupalCon Rotterdam email 1 (Aug 25).
• DrupalCamp Italy & Spain SFDC campaigns (Aug 26).
Felipe Tencio
Audiences & Reporting
• DrupalCon Rotterdam customer+prospect audience (Aug 20).
• Q3 Campaign ICP account & contact lists.
• 4 event pre/post-event audience reports.
Unassigned Queue
Needs an Owner
• 8 upcoming tasks unassigned.
• SFDC CID requests (Be the Source, Agentic Marketing).
• Best Platform for Drupal H2 ICP contact report.
Source: Asana open tasks due Aug 20–30 2026.

## Slide 15
LOOK AHEAD
Active Sub-Projects
SUB-CATEGORY
CORE ACTIVITY
OPEN
STATUS
Email(s) / Nurture Sequences
Event promo + registration + post-event sends
15
IN PROGRESS
Audiences
ICP + event audience pulls & contact lists
7
IN PROGRESS
SFDC Campaigns (single + multiple)
Campaign records + forms for events
4
ON TRACK
IT / Integration
Zapier–LinkedIn, click-ID attribution
4
BLOCKED
Form Requests
Webinar test forms + push-live
3
IN PROGRESS
List Upload
Event list uploads into SF
1
ON TRACK
Source: Asana open top-level tickets by Project Type, 2026-08-20 (53 open total).

## Slide 16
LOOK AHEAD
Incomplete / Blocked Tickets
TICKET
ASSIGNEE
MISSING INFO / REASON
PRIORITY
Zapier integration – LinkedIn
Unassigned
Blocked — needs integration scoping & owner
BLOCKED
[Event Name] Pre Event Marketing Emails
Unassigned
Require info — literal [Event Name] placeholder, no event
BLOCKED
Optimize Starter upon ACP Renewal — Cadence
Karen Plant
Require info / description
AT RISK
SFDC Campaign Request – Pantheon Compete
Aayushi
Overdue since Aug 6
AT RISK
Source Subscription Notification (Felipe)
Felipe
Overdue since Aug 13
AT RISK
SHSMD Speakers – Build List
Felipe
Overdue since Aug 19
AT RISK
Source: Asana open tickets flagged Blocked / Require-Information, or past due, as of 2026-08-20. 25 of 53 open top-level tickets are unassigned.

## Slide 17
LOOK AHEAD
Data Hygiene & Recommendations
Flagged This Period
• Naming drift: 11 of 12 new campaigns use the lowercase channel-prefix style (em_promo_, ev_workshop_, evt_webinar_), not the documented Region_Channel_Product_Description_YYYY-Qn. Only Content_Chaos_Quiz_2026-Q3 partly conforms.
• Negative pipeline: DAM Workshop Boston campaign shows AmountAllOpportunities = -$1,227 — impossible value, likely a currency/rollup anomaly.
• Literal [Event Name] placeholders persist in Asana ticket + sub-task names (event-template substitution bug) — pollutes reporting and blocks audience pulls.
• 10 of 12 new campaigns have 0 members (expected for just-built event/webinar shells; re-check after 5 business days).
Recommendations
1. Run the campaign-hygiene-audit pass on the 12 new campaigns — a single convention would restore clean reporting across all 12 rather than 1.
2. Fix the [Event Name] template substitution at source: it is currently blocking 1 unassigned email ticket and appears in live sub-task names — one template fix clears the whole event family.
3. Assign the 8 unassigned upcoming tasks (incl. Zapier–LinkedIn) before the Thursday call, so nothing due Aug 20–30 sits ownerless.
4. Verify the Boston campaign's -$1,227 opportunity rollup with RevOps — a negative pipeline figure will distort the Q3 email-influence number.
Source: Salesforce Campaign SOQL + Asana open tickets, 2026-08-20. Convention: campaign-naming skill.

## Slide 18
Questions & Discussion
Thank you — MOPS Team
Next Review: August 27, 2026 | Lead: Aayushi Sharma

## Slide 19
APPENDIX
Data & Image Sources
Connectors queried (2026-08-20)
• Asana — [MOps] Intake project (gid 1205660951274722): 37 completions Aug 13–19; 38 open tasks due Aug 20–30; 53 open top-level tickets; Email milestone sub-tasks both completion states.
• Salesforce (CRM) — Campaign SOQL, CreatedDate/StartDate = LAST_N_DAYS:7. 12 campaigns returned. Members/responses/opps/AmountAllOpportunities read directly.
• Atlassian Jira — project MOPS, updated >= 2026-08-13: 3 issues touched (MOPS-659156 click-ID attribution Need-Info/Blocked; MOPS-659158 MQL currency High; MOPS-659157 Tier-2 misroute Low). None campaign-blocking.
Data gaps & caveats
• Asana has no day-based SLA field → true "% within SLA" not computable; cycle time shown instead (intake→completion, business days).
• Region/Audience null on Email milestones → inferred from send name for slides 5 & 12.
• Boston DAM campaign AmountAllOpportunities = -$1,227 (anomaly, flagged, not corrected).
• Drive folder ID in skill (0ACqafLRVUxJzUk9PVA) did not resolve on 2026-08-13; real target corroborated as 1V3yfifgATNpZ0CJn5G5ONzJzgpgT6oj5. Google Slides upload gap persists — see notes.
• No external images used — all charts/shapes are native PowerPoint vector objects. Acquia brand palette.