## Slide 1
MOps Weekly Review
Team Performance, Campaign Results & Strategic Roadmap
September 24, 2026 | Project Review Meeting

## Slide 2
RETROSPECTIVE
Reviewing Last Week
Sep 17–23, 2026

## Slide 3
RETROSPECTIVE
Executive Summary
Sep 17–23, 2026
35
Tasks Completed
35 tasks shipped (5 requests + 30 sub-tasks) — a lighter top-line week, steady sub-task throughput
14 SFDC campaigns created/launched → 7,601 contacts + 193 leads, 7,752 responses, 87 opportunities, $365K pipeline (6 already won)
Campaign-creation SLA clean this week (no SFDC-Campaign-only builds to test); List Upload hit its 3–7 day window (6 bd) — email-type SLA compliance flagged as a measurement gap (see slide 7)
35 tasks shipped (5 requests + 30 sub-tasks) — a lighter top-line week, steady sub-task throughput
14 SFDC campaigns created/launched → 7,601 contacts + 193 leads, 7,752 responses, 87 opportunities, $365K pipeline (6 already won)
Campaign-creation SLA clean this week (no SFDC-Campaign-only builds to test); List Upload hit its 3–7 day window (6 bd) — email-type SLA compliance flagged as a measurement gap (see slide 7)
A quieter week on top-level completions after last week's 38, but sub-task volume held (30) — driven by the DrupalCon Rotterdam, Drupal Canvas/Agentic Content, and Partner Summer Party London email workstreams. Campaign creation returned to a normal weekly pace (14, vs. the prior week's 123-campaign paid-media batch), which makes the real signal easier to read: 8 of 14 new campaigns already show member activity, and the Missing Success Factor and Henry Stewart DAM/AI sends are already driving pipeline. Two new data-hygiene findings surfaced this run — a blank-name Blocked ticket created minutes before this report ran, and two “Test”-named Zoom Webinar campaigns sitting live in production — flagged on slide 17.
Source: Asana [MOPs] Intake (search_tasks, completed_on 2026-09-17–23) + Salesforce Campaign SOQL

## Slide 4
RETROSPECTIVE
Completed Tasks by Team Member
Sep 17–23, 2026
Harish Pandey
17
Felipe Tencio
8
Aayushi Sharma
6
Karen Plant
2
Kasey Pires
1
Danielle Templeton
1
Jennifer Schroback
0
Source: Asana [MOPs] Intake, search_tasks (completed=true, completed_on 2026-09-17–23), by assignee. Karen Plant/Kasey Pires/Danielle Templeton are non-MOPS collaborators who closed intake sub-tasks this week.

## Slide 5
RETROSPECTIVE
Emails Sent Last Week
Sep 17–23, 2026
SEND / CAMPAIGN NAME | SEND DATE | REGION / AUDIENCE
DAM Workshop NYC – Pre-Event Email 02 | Sep 23 | NYC / DAM Workshop
Partner Summer Party – Thank You Email | Sep 23 | London / Partners
[DrupalCon Rotterdam] 2nd Email Send | Sep 23 | EMEA / DrupalCon Rotterdam
HS Webinar Sept 24 – Email Invite 1 | Sep 22 | Not tracked (no Region field)
Webinar w/ Hounder & LADWP – Email Invite 3 | Sep 21 | LADWP
Drupal Canvas & Agentic Content – Post-Event Attendee Email | Sep 18 | Webinar attendees
Drupal Canvas & Agentic Content – Post-Event No-Show Email | Sep 18 | Webinar no-shows
[Scottish Web Folk] Email to Higher Ed | Sep 18 | Higher Ed / Scotland
September 2026 Partner Newsletter | Sep 18 | Partners
[DrupalCon Rotterdam] Partner Summit Email 3 | Sep 17 | EMEA / DrupalCon Rotterdam
Partner Summer Party – London Email 4 | Sep 17 | London / Partners
Acquia TV Manifesto – WaterAid | Sep 17 | Not tracked (no Region field)
12 sends this week (2 more completed earlier today, Sep 24, before this report ran — outside the Sep 17–23 window, not counted here).
Source: Asana Email-type milestone sub-tasks, completed with due date in retro window. “Region/Audience” has no dedicated Asana field (Requesting Team/Requestor are null on 49–50 of tickets, per intake-dispatch finding) — shown where inferable from campaign/parent name, else flagged.

## Slide 6
RETROSPECTIVE
Campaign Performance (Salesforce)
Sep 17–23, 2026
CAMPAIGN | MEMBERS | RESPONSES | RESP. RATE | LEADS/OPPS
em_promo_Missing Success Factor...2026_q3 | 5,649 | 5,649 | 100% | 2 / 70
em_nl_ac_September partner newsletter_2026_q3 | 1,182 | 1,182 | 100% | 170 / 8
em_promo_dam_sept_HenryStewart_DAM and AI_2026_q3 | 491 | 491 | 100% | 0 / 4
em_nurture_source_beyond portals emails_2026_q3 | 310 | 268 | 86% | 0 / 0
em_promo_Scottish Web Folk Conference_2026_q3 | 134 | 134 | 100% | 5 / 1
evt_ws_26_q3_all_dam workshop boston 2026 | 14 | 14 | 100% | 7 / 4
em_followup_partner summer party london...2026_q3 | 13 | 13 | 100% | 8 / 0
evt_corp_all_User Group Barcelona_2026_Q4 | 1 | 1 | 100% | 1 / 0
Period roll-up: 193 leads · 7,601 contacts · 7,752 responses · 87 opportunities · $365,385 pipeline · 6 won
Source: Salesforce SOQL, Campaign + CampaignMember (CreatedDate/StartDate = LAST_N_DAYS:7). 6 of 14 campaigns this week have zero members (2 today's new creates, 1 future-dated Planned webinar, 2 “Test” junk campaigns, 1 approaching the 5-bd hygiene threshold — see slide 17) and are omitted from this table.

## Slide 7
RETROSPECTIVE
SLA & Cycle Time
Sep 17–23, 2026
This Week
• No SFDC-Campaign-only tickets completed this week — the 1-business-day creation SLA has nothing to test against this period (clean, not a gap).
• SFDC List Upload – Febraban BR: 6 business days (created Sep 9 → completed Sep 17) — within the 3–7 day SLA window.
• 5 Email(s)-type top-level tickets closed: avg cycle time 14.6 business days (range 3–34 bd). Per sla-watchdog, Email SLA anchors to the scheduled send date, not ticket creation — this raw creation→completion span is directional only, not a pass/fail verdict. Flagging as a standing measurement gap: this report cannot compute true Email SLA compliance without a scheduled-send-date field.
• 1 Rush/Out-of-SLA ticket this week: “Customer Email: The Missing Success Factor for Growth in the Agentic Era” — flagged Rush, turned around in 3 business days.
Source: Asana created_at/completed_at on retro-window top-level completions + sla-watchdog SLA table (.claude/skills/sla-watchdog/SKILL.md).

## Slide 8
RETROSPECTIVE
Lead Weekly Wins — Aayushi Sharma
Sep 17–23, 2026
Webinar & Event Follow-through
• DAM Workshop NYC – Pre-Event Email Send 02
• Drupal Canvas & Agentic Content – Webinar Email Creation + Post-Event Attendee/No-Show Email builds
Campaign Work
• Churn customer campaign – Email Campaign
• Acquia TV Manifesto – WaterAid
Source: Asana, tasks assigned to Aayushi Sharma completed 2026-09-17–23 (6 total).

## Slide 9
RETROSPECTIVE
Team Performance Highlights
Sep 17–23, 2026
Harish Pandey
ON TRACK
• 17 tasks completed — highest volume this week
• Carried the DrupalCon Rotterdam + Partner Summer Party London email sequences end to end
• Also closed SFDC Campaign Creation, list uploads, and UTM builds
Felipe Tencio
ON TRACK
• 8 tasks completed, concentrated in Drupal Canvas & Agentic Content audience/report work
• Closed SFDC List Upload – Febraban BR (6 bd, within SLA)
• Owns audience-pull work across 4 of this week's 8 completions
Jennifer Schroback
IN PROGRESS
• 0 completions in the intake board this week
• Holds Medium-priority “Zapier integration – LinkedIn” (In Progress) — note: a second, separate ticket with the identical name is Blocked/unassigned (see slide 17)
• Manager-owner of the 3 no-pattern intake types per intake-routing
Source: Asana, tasks assigned to each member completed or open 2026-09-17–24.

## Slide 10
LOOK AHEAD
Planning Next Week
Sep 24 – Oct 3, 2026

## Slide 11
LOOK AHEAD
Upcoming Tasks by Team Member
Sep 24 – Oct 3, 2026
Unassigned
13
Harish Pandey
12
Aayushi Sharma
9
Felipe Tencio
7
Jennifer Schroback
0
Total Capacity Required: 41 Tasks (+4 already overdue as of today — see slide 16)
Source: Asana [MOPs] Intake, search_tasks (completed=false, due_on 2026-09-24–10-03), by assignee.

## Slide 12
LOOK AHEAD
Upcoming Email Sends Next Week
Sep 24 – Oct 3, 2026
SEND / CAMPAIGN NAME | SEND DATE | REGION / AUDIENCE
DrupalCamp Italy Wrap Around Event Email 1 | Sep 24 | Italy — ⚠ shares date+owner w/ row below
DrupalCamp Italy Wrap Around Event Email 2 | Sep 24 | Italy — ⚠ shares date+owner w/ row above
EDUCAUSE Wrap Around with Hounder – Send | Sep 28 | EDUCAUSE
[DrupalCon Rotterdam] Partner Summit Email 4 | Sep 28 | EMEA / DrupalCon Rotterdam
Source: Asana Email-type milestone sub-tasks, incomplete, due 2026-09-24–10-03. Both Sep 24 sends share a date AND owner (Harish Pandey) — same parent campaign (DrupalCamp Italy), so likely an intentional same-day sequence rather than an accidental clash; flagged per the skill's audience-clash rule regardless. All 4 upcoming sends this window are owned by Harish — a capacity concentration to watch.

## Slide 13
LOOK AHEAD
Priority Pipeline — Aayushi Sharma
Sep 24 – Oct 3, 2026
Board-wide Priority Snapshot
• 90% of open top-level tickets (47 of 52) have a null Priority field — the documented gap intake-routing was built to close is still live on the board.
• Only 5 tickets carry a set Priority: 2 Urgent, 2 Medium, 1 Low.
• Urgent (2): “VCCP campaign – Prospect email number 1” (Harish, due Sep 24) · “Meta Lead Forms to Salesforce integration (Conversions API setup)” (Unassigned, due Sep 18 — already overdue).
• Medium (2): “Zapier integration – LinkedIn” (Jennifer, In Progress) · “Upload Offline Leads to Salesforce” (Harish, no due date).
Source: Asana [MOPs] Intake, Priority custom field on all 52 open top-level tickets.

## Slide 14
LOOK AHEAD
Upcoming Strategic Priorities
Sep 24 – Oct 3, 2026
Harish Pandey
AT RISK
• 12 tasks due next window — highest look-ahead load
• Owns all 4 upcoming email sends (DrupalCamp Italy x2, EDUCAUSE, DrupalCon Rotterdam)
• Holds the sole Urgent ticket with a due date: VCCP campaign prospect email (due today, Sep 24)
Felipe Tencio
ON TRACK
• 7 tasks due next window
• Audience/report work continues on the Drupal Canvas & Agentic Content series
Jennifer Schroback
READY
• 0 tasks due next window on the intake board
• No-pattern intake types (IT/Integration, Automations | Martech, UAT) route to her per intake-routing — 4 open IT/Integration tickets on the board to scope
Source: Asana, tasks due 2026-09-24–10-03 by assignee + Priority/Project Type fields.

## Slide 15
LOOK AHEAD
Active Sub-Projects
Sep 24 – Oct 3, 2026
SUB-CATEGORY | CORE ACTIVITY | STATUS
Email Requests | 15 open (Email(s) only ¦ Nurture Sequences) — largest single category | IN PROGRESS
SFDC & UTM | 3 SFDC Campaigns only (multiple) open; 0 SFDC-Campaign-only completions this week | READY
Webinar Requests | 2 open Webinar Request tickets + the DrupalCamp Italy/EDUCAUSE/Rotterdam sends in flight | IN PROGRESS
List Uploads | 1 open List Upload ticket; 1 completed this week within SLA (Febraban BR) | ON TRACK
Audiences | 5 open Audiences tickets | IN PROGRESS
IT/Integration | 4 open tickets, incl. the duplicate-named Zapier–LinkedIn pair (slide 17) | AT RISK
Unclassified (null Project Type) | 14 open top-level tickets with no Project Type set | AT RISK
Source: Asana [MOPs] Intake, Project Type field grouping across all 52 open top-level tickets.

## Slide 16
LOOK AHEAD
Incomplete Tickets
Sep 24 – Oct 3, 2026
TICKET | ASSIGNEE | MISSING INFO | PRIORITY
[Event Name] Pre Event Marketing Emails | Unassigned | Email copy from Michelle Glass (asked Jul 13, ~73 days open) + live [Event Name] placeholder-name bug | BLOCKED
Zapier integration – LinkedIn (gid ...116563) | Unassigned | Blocked, no notes on what's blocking; open since Jan 12 (~255 days) | BLOCKED
Optimize Starter upon ACP Renewal – Email Cadence | Karen Plant | Awaiting 2026 priorities decision; product now owned by Melissa per Apr comment — open since Aug 2025 | BLOCKED
(blank-name ticket, gid ...882954) | Unassigned | Created 2 min before this report ran; every field blank except MOPS-Status=Blocked — likely mid-creation, not a real blocker yet | BLOCKED
EMEA - GLAM/BASE campaign - Behaviour score<50 | Unassigned | Overdue — was due Sep 23 | AT RISK
Gartner IT Symposium Pre Event Marketing Emails | Unassigned | Overdue — was due Sep 23 | AT RISK
Webinar Landing Page Updated to On Demand [MOPs] | Unassigned | Overdue — was due Sep 23 | AT RISK
Upload Webinar Recording to DAM | Unassigned | Overdue — was due Sep 23 | AT RISK
Source: Asana MOPS-Status=Blocked/Require Information (get_task_stories for reasons, not guessed) + due_on < today among open tickets.

## Slide 17
LOOK AHEAD
Data Hygiene & Recommendations
Sep 24 – Oct 3, 2026
Flags This Week
• 6 of 14 campaigns created this week (43%) have zero Campaign Members — but only 1 (DAM Workshop San Francisco, created Sep 18, ~4 bd old) is genuinely approaching the 5-business-day flag threshold. The other 5 are either today's brand-new creates, a future-dated Planned Q4 webinar, or 2 literal “Test”/“Zoom test7” campaigns that shouldn't be live in production at all.
• 0 of 14 campaigns this week are missing Type/Status/StartDate — clean on that check.
• 0 of 14 campaign names this week follow the documented Region_Channel_Product_Description_YYYY-Qn convention (campaign-naming skill) — all use the established em_/evt_ lowercase prefix pattern instead. Flagged as advisory per the skill, not a hard fail.
• New: two separate open Asana tickets are both named “Zapier integration – LinkedIn” — one Blocked/unassigned (created Jan 12), one In Progress/Jennifer Schroback/Medium priority (created Mar 2). Worth confirming whether this is duplicate work before both get worked independently.
• New: a Blocked ticket (gid 1218827173882954) was created with a blank name and every field empty 2 minutes before this report ran — likely a mid-creation artifact, not a real blocker.
Recommendations
• Retire or relabel the 2 “Test”/“Zoom test7” campaigns — removes 2 of this week's 6 zero-member campaigns from next week's hygiene count.
• Close or complete the blank-name ticket (gid ...882954) before it ages into next week's backlog with zero actionable information.
• Reassign or close “Optimize Starter upon ACP Renewal” (open 13+ months, ownership already handed to Melissa per Karen Plant's comment) — removes the oldest item from every future blocked-list scan.
Source: Salesforce Campaign SOQL (hygiene checks) + Asana MOPS-Status/task_stories (Asana findings). Naming convention: .claude/skills/campaign-naming/SKILL.md.

## Slide 18
Questions?
Next Review: October 1, 2026 | Lead: Aayushi Sharma

## Slide 19
APPENDIX
Data & Image Sources
Connectors queried this run
Sources & Gaps
• Asana [MOPs] Intake (gid 1205660951274722) — search_tasks + get_task + get_task_stories, queried 2026-09-24 ~14:10 UTC. Worked on first attempt, no auth gaps.
• Salesforce — soqlQuery against Campaign + CampaignMember, queried 2026-09-24 ~14:20 UTC. Query-only connector (no write path) — all campaign data is read, none created/edited here.
• Jira (Atlassian MOPS project) — searchJiraIssuesUsingJql, queried 2026-09-24 ~14:25 UTC. 1 new issue this week (MOPS-659161); MOPS-659156 and MOPS-659160 checked directly, both still open/unresolved.
• GAP: Region/Audience has no dedicated Asana field on [MOPs] Intake (Requesting Team + Requestor are null on ~49 of 50 recent tickets, per the intake-dispatch finding) — shown as “not tracked” or inferred from campaign name on slides 5 and 12.
• GAP: Google Slides upload not attempted this run — see the #mops-team post and the note below.
• No external images used — deck built with native pptx shapes only (no embedded bitmaps), consistent with every run since 2026-07-30.
MOps Weekly Review — generated by the mops-weekly-review-2.0 routine.